## Sheet1
Title1 | Title2 | Title3 | Title4 | Title5 | Title6 | Description1 | Description2 | Description3 | Description4 | Description5 | Description6 | Description7 | Description8 | Description9 | Description10 | Description11 | Description12 | Description13 | Description14 | Description15 | Description16 | Description17 | Description16 | Description17 | Description16 | Description17 | Description16 | Description17 | Description16 | Description17
Project | [5 empty] | It is a temporary endeavor | It creates a unique product, service or result
Stakeholders | [5 empty] | People or organizations | Are interested or impacted by the project | Impact could be positive or negative | Could be internal or external to org | What inluence they could have | Balance with project constraints
Project Management | [5 empty] | Both science and an art | Science is process, tools | Art is skills | Skills like influencing, organizing, strategizing etc.
Process | Approaches |  |  |  |  | Predictive, Agile, Hybrid
Process | Approaches | Predictive |  |  |  | Plan driven | Waterfall | Traditional
Process | Approaches | Agile |  |  |  | When scope is emerging | Change driven | Adaptive
Process | Approaches | Hybrid |  |  |  | Uses both predictive and agile
Program Management | [5 empty] | Grouping related projects | Interdependencies between projects
Portfolio Management | [5 empty] | Includes programs, projects, related ops work
Organizational Project Management | [5 empty] | framework for keeping the org focused on overall strategy | how prioritized, managed, executed and measured
Project Management Office | [5 empty] | Department that provides or ensures compliance with project governance | oversees and standardizes the mgmt of project | Manage interdependencies | Assess if achieving strategic objectives | Provide resources | Minitor compliance | Gather lessons leant and circulate | Provide templates wbs, user stories, comm plans | Provide guidance and governance | Prioritize projects
PMO | Supportive |  |  |  |  | provides policies, methodologies, templates, lessons learnt | low level of control | recommends
PMO | Controlling |  |  |  |  | Provides support and guidance | Trains | Moderate level of control
PMO | Directive |  |  |  |  | Provides PM | Responsible for results | High level of control
Business Case
Benefits management plan
Enterprise environmental factors
Organizational Process Assets
Organizational Process Assets | Types |  |  |  |  | processes, procedures and policies | Org knowledge repos
Org structure | Functional |  |  |  |  | grouped by areas of specialization
Org structure | Project oriented |  |  |  |  | grouped by projects
Org structure | Matrix |  |  |  |  | two managers
Org structure | Matrix | Strong |  |  |  | power rests with PM
Org structure | Matrix | Weak |  |  |  | power rests with functional manager
Org structure | Matrix | Balanced |  |  |  | power is shared among PM and FM
Org structure | Functional | Advantages |  |  |  | Easier management of specialists | Team members report to only one supervisor | Similar resources are centralized, as the company is grouped by specialties | Clearly defined career paths in areas of work specialization
Org structure | Functional | Disadvantages |  |  |  | People place more emphasis on their functional specialty to the detriment of the project | Limited career path in project management | The project manager has little or no authority
Org structure | Project oriented | Advantages |  |  |  | Efficient project organization | Team loyalty to the project | More efficient communications than functional | Project manager has more power to make decisions
Org structure | Project oriented | Disadvantages |  |  |  | No “home” for team members when project is completed | Lack of specialization in disciplines | Duplication of facilities and job functions | May result in less efficient use of resources
Org structure | Matrix | Advantages |  |  |  | Highly visible project objectives | Improved project manager control over resources (as compared to functional) | More support from functional areas | Maximum utilization of scarce resources | Better coordination | Better horizontal and vertical dissemination of information | Team members maintain a “home”
Org structure | Matrix | Disadvantages |  |  |  | Extra administration is required | Project team members have more than one manager | More complex to monitor and control | Resource allocation is more complex | Extensive policies and procedures are needed | Functional managers may have different priorities than project managers | Higher potential for conflict
Project Initiation | Requirements |  |  |  |  | The business case and the benefits management plan for the project. | The product description and requirements as they are known up to this point; in other words, what is the project supposed to do? | How the project fits into or supports the company’s strategic plan. | A list of likely stakeholders | Any known constraints (such as imposed schedule, budget, or resources), risks, and assumptions. | Any relevant agreements, including contracts, if any of the work will be done under contract. | Industry standards. | Marketplace trends and legal, regulatory, or compliance factors. | The company’s change control system. | Defined processes and procedures for how the company operates. | Relationships with the sponsor of the project, likely stakeholders, and possible team members. | Templates from past projects. | Historical WBSs. | Historical estimates. | Lessons learned from previous projects. | What is going on in the company today, including major projects and the potential impact that current and planned initiatives could have on this project. | An understanding of the company’s culture. | A list of people who may be good team members. | Information on organizational and project governance. | Let me know if you'd like this organized into a downloadable document or table format.
Assumption Log | [5 empty] | started when project charter is developed
Constraints | [5 empty] | imposed by management or sponsor | scope, cost, schedule, resources, risk, csat, quality | mgmt decides priority of each constraint
Data gathering | [5 empty] | benchmarking, brainstorming, prompt lists, checklists, interviews, market research questionaires and surveys
Data Analysis | [5 empty] | alternatives analysis, assumptions and constraints, cost benefit analysis, document analysis, earned value analysis, performance reviews, reserve analysis, rca, simulation, swot, trend analysis, value stream mapping, variance analysis, what if analysis
Data Representation | [5 empty] | affinity diagrams, cause and effect diagrams, control charts, flowcharts, heirarchical charts, histograms, logical data models, matrix diagrams charts, mind mapping, probability and impact matrices, release maps, scatter diagrams, stakeholder engagement assessment matrices, stakeholder mapping / representation, text oritented formats
Decision Making | [5 empty] | fist of five, multicriteria decision analysis, voting
Communication | [5 empty] | Active listening, appreciative inquiry, feedback, presentations, meeting management, communication methods, comm tech
Interpersonal team skills | [5 empty] | conflict management, cultural awareness, decision making, emotional intelligence, facilitation, influencing, leadership, meeting mgmt, motivation, negotiation, networking, observation / conversation, political awareness, team building
Estimating | [5 empty] | Analogous, Bottom up, parametric, top down, expert judgement, planning poker
Financials | ROI |  |  |  |  | Potential profitability of an investment | Benefits received relation to cost
Financials | PV |  |  |  |  | Future Value / (1 + r) power n . fv is future value, r - interest rate, n - no of time periods
Financials | NPV |  |  |  |  | PV - Initial investment
Financials | IRR |  |  |  |  | its the r in the PV formula
Financials | Payback period |  |  |  |  | time to recover its investment
Financials | Cost benefit analysis |  |  |  |  | Benefit or Revenue / Cost
Financials | EVA |  |  |  |  | economic value added.
Financials | Opportunity cost |  |  |  |  | opportunity given up by selecting one project over another
Financials | Sunk costs |  |  |  |  | expended costs
Financials | Law of diminishing returns |  |  |  |  | adding more input will not produce more output
Financials | Working capital |  |  |  |  | current assets - current liabilities
Financials | Depreciation |  |  |  |  | lose value over time
Financials | Depreciation | Straight line |  |  |  | same amount deducted every year
Financials | Depreciation | Accelerated | Double declining |  |  | rate = 2/ no of years. take out that rate% every year from book value | for e.g. book value = 100000, useful life=5 years, salvage value is 10000. so you take out 40% every year till you reach salvage value
Financials | Depreciation | Accelerated | Sum of years digits |  |  | (5/15)*(100000-10000)
Management to Leadership | [5 empty] | Tasks - People | Control - Empowerment | Efficiency - Effectiveness | Doing things right - doing the right things | speed - direction | practices - principles | command - communication
Process groups | [5 empty] | Initiating | Planning | Executing | Monitoring and Controlling | Closing
Phase Gate | [5 empty] | analyzing the results of the phase | to decide if we stop continue
Process group tasks | Initiating |  |  |  |  | Select project manager | Determine company culture and existing systems | Collect processes, procedures, and historical information | Divide large projects into phases | Understand business case | Uncover initial requirements, assumptions, risks, constraints | Assess project and product feasibility within the given constraints | Create measurable objectives and success criteria | Develop project charter | Identify stakeholders and determine their expectations, interest, influence, and impact | Request changes | Develop assumptions log | Develop stakeholder register
Process group tasks | Planning |  |  |  |  | Determine development approach, life cycle, and how you will plan for each knowledge area | Define and prioritize requirements | Create project scope statement | Assess what to purchase and create procurement documents | Determine planning team | Create WBS and WBS dictionary | Create activity list | Create network diagram | Estimate resource requirements | Estimate activity durations and costs | Determine critical path | Develop schedule | Develop budget | Determine quality standards, processes, and metrics | Determine team charter and all roles and responsibilities | Plan communications and stakeholder engagement | Perform risk identification, qualitative and quantitative risk analysis, and risk response planning | Go back—iterations | Finalize procurement strategy and documents | Create change and configuration management plans | Finalize all management plans | Develop realistic and sufficient project management plan and baselines | Gain formal approval of the plan | Hold kickoff meeting | Request changes
Process group tasks | Executing |  |  |  |  | Execute work according to the project management plan | Produce product deliverables (product scope) | Gather work performance data | Request changes | Implement only approved changes | Continuously improve; perform process improvement | Follow processes | Determine whether quality and processes are correct and effective | Perform quality audits and issue quality reports | Acquire final team and physical resources | Manage people | Evaluate team and individual performance; provide training | Hold team-building activities | Give recognition and rewards | Use issue log | Facilitate conflict resolution | Release resources as work is completed | Send and receive information, and solicit feedback | Report on project performance | Facilitate stakeholder engagement and manage expectations | Hold meetings | Evaluate sellers; negotiate and contract with sellers | Use and share project knowledge | Execute contingency plans | Update project management plan and project documents
Process group tasks | Monitoring & Controlling |  |  |  |  | Take action to monitor and control the project | Measure performance and determine variance from the plan | Measure performance against other metrics in the project management plan | Analyze and evaluate data and performance | Determine if variances warrant a corrective or change request | Influence factors that cause change | Request changes | Perform integrated change control | Approve or reject changes | Update project management plan and project documents | Inform stakeholders of all approved changes and results | Monitor stakeholder engagement | Confirm configuration compliance | Create forecasts | Gain customer’s acceptance of interim deliverables | Perform quality control | Perform risk reviews, reassessments, and audits | Manage reserves | Manage, evaluate, and close procurements | Evaluate use of physical resources
Process group tasks | Closing |  |  |  |  | Confirm work is done to requirements | Complete final procurement | Gain final acceptance of the product | Complete financial closure | Handover completed product | Solicit customer’s feedback about the project | Complete final performance reporting | Index and archive records | Gather lessons learned and update knowledge bases
Knowledge Areas | [5 empty] | Stakeholders | Scope | Schedule | Cost | Quality | Resources | Communications | Risk | Procurement
Process | Develop Project Charter |  |  |  |  | Project title and description | PM Assigned and authority level | Business Case | Resources preassigned | Key stakeholder list | High level requirements | High level product description / Key deliverables | High level assumptions | High level constraints | Measurable project objectives | Project Approval requirements | Overall project risks | Project Exit Criteria | Project Sponsors
Process | Develop Project Management Plan
Baselining | [5 empty] | It is done at scope, schedule and cost level
Process Chart | [5 empty] | [View Mermaid Diagram](https://www.mermaidchart.com/raw/1267c636-08b3-4aaa-9ee5-21b914385c66?theme=light&version=v0.1&format=svg)
Initiating | Integration Management | Develop Project Charter |  |  |  | None | Purpose: Formally authorizes the project and gives the project manager authority to apply organizational resources to project activities. It aligns the project with strategic objectives and documents key decisions to move forward. | Main Output: Project Charter | Key Elements: Project purpose, objectives, success criteria, high-level requirements, description, risks, milestones, financials, stakeholders, approval, PM authority, sponsor info | Inputs: Business Case, Benefits Management Plan, Agreements, EEFs, OPAs, Stakeholder inputs, Assumption log, Historical info | Tools & Techniques: Expert Judgment, Data Gathering, Interpersonal Skills, Meetings | Notes: Officially starts project. PM gets authority. Aligns business goals. Essential for planning and stakeholder engagement.
Initiating | Stakeholder Management | Identify Stakeholders |  |  |  | Develop Project Charter | Purpose: Identify all stakeholders who affect or are affected by the project, and analyze their influence, interest, and impact. | Main Output: Stakeholder Register | Key Elements: Identification info, influence, interest, expectations, classification (internal/external/supportive/resistant) | Inputs: Project Charter, Business Docs, Agreements, EEFs, OPAs | Tools & Techniques: Expert Judgment, Stakeholder Analysis, Data Gathering, Representation Techniques, Meetings | Notes: Foundation for engagement planning. Updated as new stakeholders are discovered or dynamics change.
Planning | Integration Management | Develop Project Management Plan |  |  |  | All subsidiary plans from Planning group must be developed | Purpose: Creates a formal, approved document that defines how the project is executed, monitored, and closed. | Main Output: Project Management Plan | Key Elements: Scope, Schedule, Cost, Quality, Resource, Communication, Risk, Procurement, Stakeholder Plans + Baselines, Tailoring decisions, Lifecycle | Inputs: Project Charter, Planning process outputs, EEFs, OPAs | Tools & Techniques: Expert Judgment, Data Gathering, Interpersonal Skills, Meetings | Notes: Central plan for all execution, monitoring, and control. Requires change control for updates.
Planning | Scope Management | Plan Scope Management |  |  |  | Develop Project Charter | Purpose: Defines how the project scope will be defined, validated, and controlled. Creates a consistent approach to prevent scope creep and missed requirements. | Main Output: Scope Management Plan, Requirements Management Plan | Key Elements: Process for preparing scope statement, maintaining WBS, approving deliverables, and handling scope changes | Inputs: Project Charter, Project Management Plan, EEFs, OPAs | Tools & Techniques: Expert Judgment, Data Analysis (alternatives analysis), Meetings | Notes: Foundation for all scope-related processes. Defines tools, roles, governance, and documentation standards for scope work.
Planning | Scope Management | Collect Requirements |  |  |  | Plan Scope Management, Identify Stakeholders | Purpose: Identifies and documents stakeholder needs and requirements to meet the project objectives. | Main Output: Requirements Documentation, Requirements Traceability Matrix | Key Elements: Functional, non-functional, business, stakeholder, and transition requirements; source tracking and acceptance criteria | Inputs: Scope Mgmt Plan, Requirements Mgmt Plan, Stakeholder Register, Business Docs | Tools & Techniques: Interviews, Focus Groups, Facilitated Workshops, Questionnaires, Prototypes, Observation | Notes: Accurate requirements gathering is key to scope control. Requirements are traced throughout the project lifecycle for validation and alignment.
Planning | Scope Management | Define Scope |  |  |  | Collect Requirements | Purpose: Develops a detailed project and product description, defining boundaries of what is and is not included. | Main Output: Project Scope Statement | Key Elements: Product scope description, deliverables, assumptions, constraints, exclusions, and acceptance criteria | Inputs: Project Charter, Requirements Documentation, OPAs | Tools & Techniques: Expert Judgment, Product Analysis, Alternatives Generation, Facilitated Workshops | Notes: The Scope Statement is critical for controlling scope and managing stakeholder expectations.
Planning | Scope Management | Create WBS |  |  |  | Define Scope | Purpose: Breaks down project deliverables into smaller, more manageable components (work packages). | Main Output: Scope Baseline (includes WBS, WBS Dictionary, Scope Statement) | Key Elements: Work packages, WBS structure, Control accounts, Deliverables, Decomposition | Inputs: Scope Management Plan, Project Scope Statement, Requirements Documentation, EEFs, OPAs | Tools & Techniques: Decomposition, Expert Judgment | Notes: Provides framework for schedule, cost, and resource planning. Helps assign responsibilities and track progress.
Planning | Schedule Management | Plan Schedule Management |  |  |  | Develop Project Management Plan | Purpose: Defines how the schedule will be planned, developed, managed, and controlled. | Main Output: Schedule Management Plan | Key Elements: Scheduling methodology, accuracy, units of measure, reporting formats, rules for performance measurement | Inputs: Project Charter, Project Management Plan, EEFs, OPAs | Tools & Techniques: Expert Judgment, Analytical Techniques, Meetings | Notes: Guides the entire schedule planning and control process. Tailored to complexity of project.
Planning | Schedule Management | Define Activities |  |  |  | Create WBS | Purpose: Identifies the specific actions required to produce project deliverables. | Main Output: Activity List, Activity Attributes, Milestone List | Key Elements: Activities, deliverables, decomposition, rolling wave planning | Inputs: Schedule Management Plan, Scope Baseline, EEFs, OPAs | Tools & Techniques: Decomposition, Rolling Wave Planning, Expert Judgment | Notes: Enables time estimation and sequencing. Milestones define significant events, not duration.
Planning | Schedule Management | Sequence Activities |  |  |  | Define Activities | Purpose: Determines logical relationships among activities to form project timeline. | Main Output: Project Schedule Network Diagram | Key Elements: Precedence Diagramming Method (PDM), leads, lags, dependencies (FS, SS, FF, SF) | Inputs: Schedule Management Plan, Activity List, Activity Attributes, Milestone List, Project Scope Statement, EEFs, OPAs | Tools & Techniques: Precedence Diagramming Method, Dependency Determination, Leads and Lags, Project Management Information System (PMIS) | Notes: Creates visual flow of tasks. Crucial for identifying critical path later.
Planning | Schedule Management | Estimate Activity Durations |  |  |  | Sequence Activities | Purpose: Approximates the number of work periods needed to complete each activity. | Main Output: Duration Estimates, Basis of Estimates | Key Elements: Effort estimates, assumptions, constraints, contingency reserves | Inputs: Schedule Management Plan, Activity List, Activity Attributes, Resource Calendars, Resource Breakdown Structure, EEFs, OPAs | Tools & Techniques: Expert Judgment, Analogous Estimating, Parametric Estimating, Three-Point Estimating, Reserve Analysis | Notes: Influences project timeline and helps in realistic schedule development.
Planning | Schedule Management | Develop Schedule |  |  |  | Estimate Activity Durations | Purpose: Analyzes activity sequences, durations, resource requirements, and constraints to create the project schedule. | Main Output: Project Schedule, Schedule Baseline | Key Elements: Gantt chart, network diagram, milestone chart, start and finish dates, critical path, float | Inputs: Schedule Management Plan, Activity List, Duration Estimates, Project Calendars, Resource Info, Risk Register | Tools & Techniques: Critical Path Method, Schedule Compression (Crashing, Fast Tracking), PMIS, Resource Optimization, What-If Analysis | Notes: Schedule Baseline becomes part of the Performance Measurement Baseline. Updated through change control process.
Planning | Cost Management | Plan Cost Management |  |  |  | Develop Project Management Plan | Purpose: Establishes policies, procedures, and documentation for planning, managing, and controlling project costs. | Main Output: Cost Management Plan | Key Elements: Units of measure, rules of performance measurement, reporting formats, precision, accuracy | Inputs: Project Charter, PM Plan, EEFs, OPAs | Tools & Techniques: Expert Judgment, Data Analysis, Meetings | Notes: Helps standardize cost estimating and control. Sets framework for the cost baseline.
Planning | Cost Management | Estimate Costs |  |  |  | Plan Cost Management | Purpose: Develops an approximation of the monetary resources needed to complete project activities. | Main Output: Cost Estimates, Basis of Estimates | Key Elements: Direct and indirect costs, contingency reserves, assumptions, constraints, cost of quality | Inputs: Cost Management Plan, Scope Baseline, Resource Requirements, Risk Register, EEFs, OPAs | Tools & Techniques: Analogous Estimating, Parametric Estimating, Bottom-Up Estimating, Three-Point Estimating, Reserve Analysis | Notes: Estimate accuracy improves with project progress. Used to build cost baseline and funding requirements.
Planning | Cost Management | Determine Budget |  |  |  | Estimate Costs | Purpose: Aggregates cost estimates to establish an authorized cost baseline. | Main Output: Cost Baseline, Project Funding Requirements | Key Elements: Funding limits, cash flow projections, time-phased budgets, contingency and management reserves | Inputs: Cost Estimates, Basis of Estimates, Schedule, Risk Register, Agreements, EEFs, OPAs | Tools & Techniques: Cost Aggregation, Funding Limit Reconciliation, Reserve Analysis, Expert Judgment | Notes: Cost baseline is used to measure and monitor cost performance. Used in Earned Value Management.
Planning | Quality Management | Plan Quality Management |  |  |  | Develop Project Management Plan | Purpose: Identifies quality requirements and standards for the project and product, and documents how they will be met. | Main Output: Quality Management Plan, Quality Metrics | Key Elements: Quality standards, continuous improvement, quality tools, quality assurance vs. control | Inputs: PM Plan, Stakeholder Register, Risk Register, Requirements Docs, EEFs, OPAs | Tools & Techniques: Cost-Benefit Analysis, Cost of Quality (CoQ), Seven Basic Quality Tools, Benchmarking, Design for X (DfX) | Notes: Defines quality strategy. Guides assurance and control. Affects scope, cost, and resource decisions.
Planning | Resource Management | Plan Resource Management |  |  |  | Develop Project Management Plan | Purpose: Defines how project resources (human and physical) will be estimated, acquired, managed, and controlled. | Main Output: Resource Management Plan, Team Charter | Key Elements: Roles and responsibilities, reporting structure, staff acquisition, training needs, recognition plans | Inputs: Project Charter, PM Plan, EEFs, OPAs | Tools & Techniques: Expert Judgment, Data Representation (hierarchies, matrices), Organizational Theory, Meetings | Notes: Team Charter defines team norms, values, communication, and working agreements. Guides future resource planning.
Planning | Communications Management | Plan Communications Management |  |  |  | Develop Project Management Plan | Purpose: Establishes how communication will be planned, structured, monitored, and controlled. | Main Output: Communications Management Plan | Key Elements: Stakeholder communication requirements, technology, methods, frequency, escalation process | Inputs: PM Plan, Stakeholder Register, EEFs, OPAs | Tools & Techniques: Communication Requirements Analysis, Communication Technology, Models, Methods, Interpersonal Skills | Notes: Vital for stakeholder engagement and team alignment. Affects information flow and perception of project success.
Planning | Risk Management | Plan Risk Management |  |  |  | Develop Project Management Plan | Purpose: Defines how to conduct risk management activities and sets the tone for risk handling across the project. | Main Output: Risk Management Plan | Key Elements: Methodology, roles and responsibilities, timing, risk categories, definitions of probability and impact | Inputs: Project Charter, PM Plan, Stakeholder Register, EEFs, OPAs | Tools & Techniques: Expert Judgment, Data Analysis, Meetings | Notes: Helps standardize and tailor risk approach. Ensures consistency across identify, analyze, and respond steps.
Planning | Risk Management | Identify Risks |  |  |  | Plan Risk Management | Purpose: Identifies individual project risks and sources of overall project risk, and documents characteristics. | Main Output: Risk Register, Risk Report | Key Elements: List of risks, root causes, triggers, categories, potential responses, risk owners | Inputs: Risk Management Plan, PM Plan components, documents, Agreements, EEFs, OPAs | Tools & Techniques: Brainstorming, Checklists, Interviews, SWOT Analysis, Assumption and Constraint Analysis | Notes: Foundation for all risk analysis. Reviewed regularly as project evolves and new risks emerge.
Planning | Risk Management | Perform Qualitative Risk Analysis |  |  |  | Identify Risks | Purpose: Prioritizes individual project risks for further analysis or action based on probability and impact. | Main Output: Updated Risk Register (with qualitative data) | Key Elements: Risk probability and impact ratings, urgency, proximity, manageability, detectability, categorization | Inputs: Risk Register, Risk Management Plan, Stakeholder Register, EEFs, OPAs | Tools & Techniques: Risk Probability and Impact Assessment, Probability-Impact Matrix, Expert Judgment, Interpersonal Skills | Notes: Enables focus on high-priority risks. Helps decide which risks need further quantitative analysis or immediate response.
Planning | Risk Management | Perform Quantitative Risk Analysis |  |  |  | Perform Qualitative Risk Analysis | Purpose: Numerically analyzes the combined effect of identified risks on project objectives. | Main Output: Updated Risk Register, Risk Report (quantitative findings) | Key Elements: Probabilistic analysis, impact on schedule and cost, confidence levels, prioritized risk list | Inputs: Risk Register, Risk Management Plan, Cost and Schedule Estimates, EEFs, OPAs | Tools & Techniques: Simulation (Monte Carlo), Sensitivity Analysis, Decision Tree Analysis, Expert Judgment | Notes: Provides data for contingency reserves and backup planning. Performed only when necessary due to cost and effort.
Planning | Risk Management | Plan Risk Responses |  |  |  | Perform Quantitative Risk Analysis | Purpose: Develops options and actions to enhance opportunities and reduce threats to project objectives. | Main Output: Updated Risk Register, Change Requests | Key Elements: Response strategies for threats (avoid, transfer, mitigate, accept) and opportunities (exploit, enhance, share, accept) | Inputs: Risk Register, Risk Report, PM Plan, OPAs | Tools & Techniques: Expert Judgment, Data Gathering, Interpersonal Skills, Strategies for Threats and Opportunities | Notes: Clear ownership and actions for each risk. Sets up implementation in Executing process group.
Planning | Procurement Management | Plan Procurement Management |  |  |  | Develop Project Management Plan | Purpose: Determines procurement approach and documents decisions about acquiring products, services, or results from outside. | Main Output: Procurement Management Plan, Procurement Strategy, Bid Documents, Source Selection Criteria, Make-or-Buy Decisions | Key Elements: Contract types (FP, T&M, CR), supplier evaluation methods, standard terms and conditions | Inputs: Project Charter, Business Docs, PM Plan, Requirements Docs, Risk Register, EEFs, OPAs | Tools & Techniques: Make-or-Buy Analysis, Expert Judgment, Market Research, Meetings | Notes: Helps ensure appropriate legal, financial, and schedule controls when outsourcing work.
Planning | Stakeholder Management | Plan Stakeholder Engagement |  |  |  | Identify Stakeholders | Purpose: Develops strategies to effectively engage stakeholders throughout the project lifecycle. | Main Output: Stakeholder Engagement Plan | Key Elements: Current vs. desired engagement levels (unaware, resistant, neutral, supportive, leading), strategies and actions for engagement | Inputs: Stakeholder Register, PM Plan, EEFs, OPAs | Tools & Techniques: Expert Judgment, Data Gathering (surveys, interviews), Data Representation (engagement matrix) | Notes: Stakeholder buy-in is critical. This plan drives communications and relationship-building efforts.
Executing | Integration Management | Direct and Manage Project Work |  |  |  | Develop Project Management Plan | Purpose: Leads and performs the work defined in the PM Plan and implements approved changes to achieve objectives. | Main Output: Deliverables, Work Performance Data, Change Requests, Issue Log | Key Elements: Deliverable creation, approved change implementation, team coordination, knowledge application | Inputs: PM Plan, Approved Change Requests, EEFs, OPAs | Tools & Techniques: Expert Judgment, PMIS, Meetings | Notes: Central execution engine of the project. Drives updates to plans and inputs for monitoring/control.
Executing | Integration Management | Manage Project Knowledge |  |  |  | Direct and Manage Project Work | Purpose: Leverages existing knowledge and creates new knowledge to support project and organizational learning. | Main Output: Lessons Learned Register | Key Elements: Explicit vs. tacit knowledge, continuous learning, best practices, knowledge sharing | Inputs: PM Plan, Deliverables, Lessons Learned, EEFs, OPAs | Tools & Techniques: Knowledge Management, Information Management, Expert Judgment | Notes: Helps avoid repeated mistakes. Builds knowledge base for future projects and decisions.
Executing | Quality Management | Manage Quality |  |  |  | Plan Quality Management | Purpose: Translates quality plan into executable activities that incorporate quality into deliverables and processes. | Main Output: Quality Reports, Test and Evaluation Documents, Change Requests | Key Elements: Design of experiments, quality audits, process analysis, quality improvements | Inputs: Quality Management Plan, Project Documents, OPAs | Tools & Techniques: Quality Audits, Design for X, Process Analysis, Root Cause Analysis | Notes: Often confused with control quality (which checks results). Manage Quality is proactive and process-focused.
Executing | Resource Management | Acquire Resources |  |  |  | Plan Resource Management | Purpose: Secures the team members, equipment, materials, and facilities needed to perform the project work. | Main Output: Physical Resource Assignments, Project Team Assignments, Resource Calendars | Key Elements: Internal vs. external acquisition, negotiation, pre-assignment, virtual team setup | Inputs: Resource Management Plan, Procurement Docs, EEFs, OPAs | Tools & Techniques: Decision Making, Interpersonal Skills, Pre-assignment, Negotiation | Notes: Resource shortages or conflicts can affect project timelines. May trigger procurement.
Executing | Resource Management | Develop Team |  |  |  | Acquire Resources | Purpose: Improves team competencies, interaction, and overall environment to enhance performance. | Main Output: Team Performance Assessments | Key Elements: Training, team-building, recognition, co-location, communication improvement, conflict resolution | Inputs: Resource Management Plan, Project Docs, EEFs, OPAs | Tools & Techniques: Team-building Activities, Training, Individual & Team Assessments, Ground Rules | Notes: Strong teams lead to better productivity. Involves soft skills and leadership.
Executing | Resource Management | Manage Team |  |  |  | Develop Team | Purpose: Tracks team performance, provides feedback, resolves issues, and manages changes to optimize performance. | Main Output: Change Requests, Project Management Plan Updates | Key Elements: Conflict resolution, issue tracking, motivation, performance assessments, coaching | Inputs: Resource Management Plan, Team Assignments, Performance Reports, OPAs | Tools & Techniques: Conflict Management, Decision Making, Emotional Intelligence, Leadership | Notes: PM must balance leadership and management. Influences morale and productivity directly.
Executing | Communications Management | Manage Communications |  |  |  | Plan Communications Management | Purpose: Ensures timely and appropriate collection, creation, distribution, storage, and disposition of project information. | Main Output: Project Communications | Key Elements: Real-time updates, targeted messaging, stakeholder-specific info needs, performance reporting | Inputs: Communications Management Plan, Work Performance Reports, EEFs, OPAs | Tools & Techniques: Communication Technology, Communication Methods, Interpersonal and Team Skills, PMIS | Notes: Frequent updates reduce stakeholder uncertainty. Tailoring messages improves engagement and clarity.
Executing | Risk Management | Implement Risk Responses |  |  |  | Plan Risk Responses | Purpose: Implements agreed-upon risk response plans to address identified individual and overall project risks. | Main Output: Change Requests, Issue Log, Risk Register Updates | Key Elements: Risk owners, response actions, fallback plans, risk triggers, residual risks | Inputs: Risk Management Plan, Risk Register, Risk Report, OPAs | Tools & Techniques: Expert Judgment, PMIS, Interpersonal and Team Skills | Notes: Effectiveness of this step impacts whether risks are truly mitigated or transferred. Requires monitoring.
Executing | Procurement Management | Conduct Procurements |  |  |  | Plan Procurement Management | Purpose: Obtains seller responses, selects a seller, and awards a contract. | Main Output: Selected Sellers, Agreements, Resource Calendars, Change Requests | Key Elements: Bid evaluation, bidder conferences, proposal scoring, negotiation, contract award | Inputs: Procurement Management Plan, Bid Docs, Seller Proposals, OPAs, EEFs | Tools & Techniques: Advertising, Bidder Conferences, Proposal Evaluation, Negotiation | Notes: Legal and financial scrutiny is high. Proper documentation ensures enforceability and risk mitigation.
Executing | Stakeholder Management | Manage Stakeholder Engagement |  |  |  | Plan Stakeholder Engagement | Purpose: Communicates and works with stakeholders to meet their needs, manage expectations, and foster engagement. | Main Output: Change Requests, Issue Log, Stakeholder Register Updates | Key Elements: Stakeholder feedback, conflict resolution, trust-building, continuous engagement | Inputs: Stakeholder Engagement Plan, Communications Plan, Issue Log, Risk Register, OPAs | Tools & Techniques: Interpersonal Skills, Communication Techniques, Ground Rules, Feedback Collection | Notes: Critical for change adoption, risk buy-in, and maintaining support across lifecycle.
Monitoring & Controlling | Integration Management | Monitor and Control Project Work |  |  |  | Direct and Manage Project Work | Purpose: Tracks, reviews, and reports progress to meet performance objectives defined in the PM Plan. | Main Output: Work Performance Reports, Change Requests | Key Elements: Variance analysis, trend analysis, earned value, forecasting, root cause analysis | Inputs: PM Plan, Schedule Forecasts, Cost Forecasts, Work Performance Information, OPAs | Tools & Techniques: Data Analysis, Decision Making, PMIS, Expert Judgment | Notes: Acts as the central feedback loop for all monitoring. Key to proactive adjustments.
Monitoring & Controlling | Integration Management | Perform Integrated Change Control |  |  |  | Monitor and Control Project Work | Purpose: Reviews all change requests, approves or rejects them, and manages changes to project documents, deliverables, and baselines. | Main Output: Approved Change Requests, Change Log | Key Elements: Change control board (CCB), configuration management, impact assessment, status tracking | Inputs: Change Requests, PM Plan, Work Performance Reports, EEFs, OPAs | Tools & Techniques: Expert Judgment, Change Control Tools, Data Analysis, Meetings | Notes: Ensures changes are aligned with business goals and project plans. Central to scope, schedule, and cost integrity.
Monitoring & Controlling | Scope Management | Validate Scope |  |  |  | Define Scope | Purpose: Formalizes acceptance of completed deliverables by the customer or sponsor. | Main Output: Accepted Deliverables, Change Requests, Work Performance Information | Key Elements: Deliverable inspection, sign-off, approval criteria, variance detection | Inputs: Verified Deliverables, Requirements Documentation, Scope Baseline | Tools & Techniques: Inspection, Decision Making, Work Performance Data Analysis | Notes: Validates product correctness with stakeholder expectations. Often triggers final payments or handovers.
Monitoring & Controlling | Scope Management | Control Scope |  |  |  | Validate Scope | Purpose: Monitors project and product scope and manages changes to the scope baseline. | Main Output: Work Performance Information, Change Requests | Key Elements: Scope creep monitoring, variance analysis, change log updates | Inputs: Scope Baseline, Requirements Docs, Work Performance Data | Tools & Techniques: Data Analysis, Variance Analysis, Trend Analysis | Notes: Controls what is and isn't delivered. Prevents gold plating and unapproved expansions.
Monitoring & Controlling | Schedule Management | Control Schedule |  |  |  | Develop Schedule | Purpose: Monitors the status of project activities to update progress and manage schedule baseline changes. | Main Output: Schedule Forecasts, Change Requests, Work Performance Info | Key Elements: Critical path, float, milestone tracking, actual vs planned dates | Inputs: Schedule Baseline, Project Calendars, Work Performance Data | Tools & Techniques: Schedule Compression, PMIS, Performance Reviews, Trend Analysis | Notes: Provides visibility into delays and recovery options. Supports accurate forecasting.
Monitoring & Controlling | Cost Management | Control Costs |  |  |  | Determine Budget | Purpose: Monitors cost performance to detect and understand cost variances from the budget baseline. | Main Output: Cost Forecasts, Work Performance Information, Change Requests | Key Elements: Earned value analysis (CPI, SPI), budget variance, forecast to complete | Inputs: Cost Baseline, Project Funding Requirements, Work Performance Data | Tools & Techniques: EVM, Forecasting, To-Complete Performance Index (TCPI), PMIS | Notes: Ensures financial control and budget integrity. Aids in proactive reallocation and escalation.
Monitoring & Controlling | Quality Management | Control Quality |  |  |  | Manage Quality | Purpose: Monitors and records results of executing quality activities to assess performance and ensure outputs meet expectations. | Main Output: Quality Control Measurements, Verified Deliverables, Change Requests | Key Elements: Inspection, testing, defect repair, cause analysis, control charts | Inputs: Quality Metrics, Deliverables, Work Performance Data, Approved Change Requests | Tools & Techniques: Inspection, Statistical Sampling, Control Charts, Quality Checklists | Notes: Helps determine whether processes are producing acceptable outputs. May identify rework needs.
Monitoring & Controlling | Resource Management | Control Resources |  |  |  | Acquire Resources | Purpose: Ensures that the physical resources assigned and allocated to the project are available as planned. | Main Output: Work Performance Information, Change Requests, Resource Updates | Key Elements: Usage monitoring, resource variances, corrective actions | Inputs: Resource Management Plan, Work Performance Data, Issue Log | Tools & Techniques: Performance Reviews, Variance Analysis, PMIS | Notes: Focuses on physical resources (not people). Helps prevent bottlenecks and shortages.
Monitoring & Controlling | Communications Management | Monitor Communications |  |  |  | Manage Communications | Purpose: Ensures information needs of project stakeholders are met through monitoring and improvement of communication activities. | Main Output: Work Performance Information, Change Requests, Updates to Plans and Docs | Key Elements: Feedback collection, information flow effectiveness, stakeholder satisfaction | Inputs: Communications Management Plan, Project Documents, Work Performance Data | Tools & Techniques: Observation, Communication Methods, PMIS, Interpersonal Skills | Notes: Reveals gaps in message delivery or misunderstandings. Helps adapt future communication.
Monitoring & Controlling | Risk Management | Monitor Risks |  |  |  | Implement Risk Responses | Purpose: Tracks identified risks, monitors residual risks, identifies new risks, and evaluates risk process effectiveness. | Main Output: Risk Register Updates, Risk Report, Change Requests | Key Elements: Trigger conditions, updated probabilities, risk audits, status reporting | Inputs: Risk Management Plan, Risk Register, Work Performance Data | Tools & Techniques: Risk Audits, Reserve Analysis, Technical Performance Measurement, Meetings | Notes: Keeps risk planning alive and responsive to changes in the project or environment.
Monitoring & Controlling | Procurement Management | Control Procurements |  |  |  | Conduct Procurements | Purpose: Manages procurement relationships, monitors contract performance, and makes changes as needed. | Main Output: Closed Procurements, Work Performance Info, Change Requests | Key Elements: Claims management, payment systems, contract updates, inspection and audits | Inputs: Procurement Docs, Agreements, Work Performance Data, Approved Change Requests | Tools & Techniques: Contract Change Control System, Claims Administration, Performance Reviews | Notes: Ensures vendors meet obligations and any disputes or adjustments are handled effectively.
Monitoring & Controlling | Stakeholder Management | Monitor Stakeholder Engagement |  |  |  | Manage Stakeholder Engagement | Purpose: Monitors overall project stakeholder relationships and adjusts strategies and plans for engaging stakeholders. | Main Output: Work Performance Information, Change Requests, Plan Updates | Key Elements: Stakeholder sentiment, feedback, engagement gap analysis, adaptation | Inputs: Stakeholder Engagement Plan, Communications Plan, Risk Register, Issue Log | Tools & Techniques: Feedback, Interviews, Comparative Analysis, Expert Judgment | Notes: Helps maintain alignment, satisfaction, and cooperation across changing stakeholder expectations.
Closing | Integration Management | Close Project or Phase |  |  |  | Perform Integrated Change Control | Purpose: Finalizes all activities to formally close the project or a phase and hand off deliverables. | Main Output: Final Product, Service, or Result Transition; Final Report; Updates to OPAs | Key Elements: Formal acceptance, contract closure, archive, knowledge transfer, lessons learned | Inputs: Accepted Deliverables, PM Plan, Project Docs, Agreements, Procurement Closure | Tools & Techniques: Expert Judgment, Data Analysis, Meetings | Notes: Ensures formal stakeholder sign-off and captures historical data for future use. Final step of the project lifecycle.
Initiating | Integration Management | Develop Project Charter |  |  |  | Why – Purpose/Need of this process in a project context: To formally authorize the project and give the project manager authority to apply organizational resources to project activities. | What – Clear definition of what happens in this process: The project is initiated through a document that outlines objectives, high-level requirements, milestones, risks, stakeholders, and a summary budget. | How – Steps involved and techniques used in execution: Meet with stakeholders; use expert judgment, data gathering, brainstorming; identify project goals, constraints, and high-level risks. | When – At what stage/time this process is initiated in the lifecycle: At the very beginning of the project, before any detailed planning begins. | Where – Where this process is applied or found: Usually initiated by the project sponsor and documented in the project charter stored in the project repository or PMO system. | Main Inputs: Business documents, agreements, EEFs, OPAs | Main Outputs: Project Charter | Key Tools & Techniques: Expert Judgment, Data Gathering, Interpersonal and Team Skills, Meetings | Key Documents Produced or Referenced: Project Charter, Business Case, Agreements | Stakeholders Involved: Sponsor, Customer, Project Manager, PMO | Dependencies (Previous and Next Processes): None before; next is Identify Stakeholders | Custom Column 1: KPIs or Success Metrics: Project charter approved and signed off | Custom Column 2: Risks If Skipped: Lack of authority for PM, unclear objectives, stakeholder misalignment | Custom Column 3: Practical Example or Case: A telecom company initiates a new 5G rollout and uses a charter to define scope, key players, budget, and timeline. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Don’t confuse the project charter with the project plan; the charter gives authority and direction, the plan details execution. | : | : | :
Initiating | Stakeholder Management | Identify Stakeholders |  |  |  | Why – Purpose/Need of this process in a project context: To ensure all stakeholders are identified, analyzed, and appropriately engaged throughout the project. | What – Clear definition of what happens in this process: Stakeholders are identified and documented along with relevant information like interest, influence, and impact. | How – Steps involved and techniques used in execution: Conduct stakeholder analysis using power-interest grids, influence-impact matrices, gather input from experts, review documentation. | When – At what stage/time this process is initiated in the lifecycle: Initiated early in the project after the charter is developed. | Where – Where this process is applied or found: Occurs in stakeholder management planning and logged in stakeholder register. | Main Inputs: Project Charter, Business documents, EEFs, OPAs | Main Outputs: Stakeholder Register | Key Tools & Techniques: Expert Judgment, Data Gathering, Data Analysis, Meetings | Key Documents Produced or Referenced: Stakeholder Register, Power/Interest Grid | Stakeholders Involved: Project Manager, Sponsor, Customers, SMEs | Dependencies (Previous and Next Processes): Follows Develop Project Charter; precedes Plan Stakeholder Engagement | Custom Column 1: KPIs or Success Metrics: Stakeholder register is complete and validated | Custom Column 2: Risks If Skipped: Missed expectations, resistance to project progress, unaddressed concerns | Custom Column 3: Practical Example or Case: A city infrastructure project maps 200+ stakeholders from local government, vendors, and public groups. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Remember stakeholder influence varies over time—continually update the register. | : | : | :
Planning | Integration Management | Develop Project Management Plan |  |  |  | Why – Purpose/Need of this process in a project context: To define the basis for all project work and how the work will be performed, monitored, and controlled. | What – Clear definition of what happens in this process: The process consolidates and integrates all subsidiary management plans into a comprehensive project management plan. | How – Steps involved and techniques used in execution: Gather all component plans, conduct planning sessions, review requirements, integrate baselines, and gain approvals. | When – At what stage/time this process is initiated in the lifecycle: At the beginning of the Planning process group, after the project charter is approved. | Where – Where this process is applied or found: In the project planning phase and maintained throughout the project in the project repository. | Main Inputs: Project Charter, Outputs from other planning processes, EEFs, OPAs | Main Outputs: Project Management Plan | Key Tools & Techniques: Expert Judgment, Data Gathering, Interpersonal and Team Skills, Meetings | Key Documents Produced or Referenced: Project Management Plan with baselines and subsidiary plans | Stakeholders Involved: Project Manager, Team Leads, Functional Managers, Sponsor | Dependencies (Previous and Next Processes): Follows project charter and stakeholder identification; precedes all planning processes | Custom Column 1: KPIs or Success Metrics: All required components are included, approved, and baselined | Custom Column 2: Risks If Skipped: No guidance for execution or control, misalignment between teams, poor scope/time/cost integration | Custom Column 3: Practical Example or Case: For a construction project, the project plan includes scope baseline, cost plan, and stakeholder engagement plan. | Notes/Tips – Common pitfalls, exam traps, or pro tips: This is not a one-time document—update it as changes occur; includes change management process. | : | : | :
Planning | Scope Management | Plan Scope Management |  |  |  | Why – Purpose/Need of this process in a project context: To establish how the scope will be defined, validated, and controlled. | What – Clear definition of what happens in this process: Defines how scope will be managed, including preparation of scope statement, WBS, and how scope changes will be handled. | How – Steps involved and techniques used in execution: Review project charter, meet with stakeholders, document scope management procedures. | When – At what stage/time this process is initiated in the lifecycle: Early in the Planning phase, before defining and decomposing the scope. | Where – Where this process is applied or found: Included in the project management plan and used across planning and control processes. | Main Inputs: Project Charter, Project Management Plan, EEFs, OPAs | Main Outputs: Scope Management Plan, Requirements Management Plan | Key Tools & Techniques: Expert Judgment, Data Analysis, Meetings | Key Documents Produced or Referenced: Scope Management Plan, Requirements Plan | Stakeholders Involved: Project Manager, SMEs, Business Analyst, Sponsor | Dependencies (Previous and Next Processes): Follows Project Management Plan; precedes Collect Requirements | Custom Column 1: KPIs or Success Metrics: Clear procedures for managing scope and requirements documented | Custom Column 2: Risks If Skipped: Scope creep, unclear work boundaries, disputes on deliverables | Custom Column 3: Practical Example or Case: In a software project, defines that all feature requests must be approved through change control board. | Notes/Tips – Common pitfalls, exam traps, or pro tips: This plan sets the stage for scope control—don’t confuse with the actual scope statement. | : | : | :
Planning | Scope Management | Collect Requirements |  |  |  | Why – Purpose/Need of this process in a project context: To gather and document stakeholders' needs and expectations for the project deliverables. | What – Clear definition of what happens in this process: Detailed and measurable stakeholder requirements are collected and documented. | How – Steps involved and techniques used in execution: Interviews, workshops, focus groups, surveys, observation, prototyping, and group decision-making techniques. | When – At what stage/time this process is initiated in the lifecycle: After the Scope Management Plan is created and before defining the scope. | Where – Where this process is applied or found: Across stakeholder engagement and requirements definition activities. | Main Inputs: Scope Management Plan, Requirements Management Plan, Stakeholder Register | Main Outputs: Requirements Documentation, Requirements Traceability Matrix | Key Tools & Techniques: Interviews, Questionnaires, Workshops, Benchmarking, Prototypes | Key Documents Produced or Referenced: Requirements Document, RTM, Interview Notes | Stakeholders Involved: Customers, End Users, Project Manager, Business Analysts, SMEs | Dependencies (Previous and Next Processes): Follows Plan Scope Management; precedes Define Scope | Custom Column 1: KPIs or Success Metrics: All major stakeholder requirements identified and traced | Custom Column 2: Risks If Skipped: Incomplete requirements, dissatisfied customers, costly rework | Custom Column 3: Practical Example or Case: During a banking software upgrade, clients were interviewed to identify regulatory reporting needs. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Don’t just document requirements—trace them throughout the project using RTM. | : | : | :
Planning | Schedule Management | Estimate Activity Durations |  |  |  | Why – Purpose/Need of this process in a project context: To estimate the time required to complete each activity to support the development of the overall project schedule. | What – Clear definition of what happens in this process: Estimates for the duration of each scheduled activity are developed using input from team members and historical data. | How – Steps involved and techniques used in execution: Use expert judgment, analogous or parametric estimating, three-point estimates, and reserve analysis. | When – At what stage/time this process is initiated in the lifecycle: After sequencing activities and identifying resources. | Where – Where this process is applied or found: Used in the schedule baseline and time tracking tools. | Main Inputs: Schedule Management Plan, Activity List, Activity Attributes, Resource Calendars | Main Outputs: Duration Estimates, Basis of Estimates, Project Document Updates | Key Tools & Techniques: Expert Judgment, Analogous Estimating, Parametric Estimating, Three-Point Estimating, Reserve Analysis | Key Documents Produced or Referenced: Basis of Estimates, Duration Log | Stakeholders Involved: Project Manager, Team Members, Estimators | Dependencies (Previous and Next Processes): Follows Sequence Activities; precedes Develop Schedule | Custom Column 1: KPIs or Success Metrics: Duration estimates documented with rationale and accuracy range | Custom Column 2: Risks If Skipped: Inaccurate schedule, resource bottlenecks, delayed delivery | Custom Column 3: Practical Example or Case: Software team estimates UI module to take 5±2 days using three-point estimation. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Understand the difference between duration and effort; always note assumptions behind estimates. | : | : | :
Planning | Schedule Management | Develop Schedule |  |  |  | Why – Purpose/Need of this process in a project context: To analyze activity sequences, durations, and resource constraints to create a realistic project schedule. | What – Clear definition of what happens in this process: The finalized project schedule is developed in the form of a Gantt chart or schedule model. | How – Steps involved and techniques used in execution: Use critical path method, schedule compression, resource optimization, and what-if scenarios. | When – At what stage/time this process is initiated in the lifecycle: After duration estimates are completed. | Where – Where this process is applied or found: Part of the schedule baseline; shared with stakeholders for tracking. | Main Inputs: Schedule Management Plan, Activity List, Duration Estimates, Resource Calendars | Main Outputs: Schedule Baseline, Project Schedule, Schedule Data, Project Calendar | Key Tools & Techniques: Critical Path Method, Resource Optimization, Schedule Compression, Simulation, Leads and Lags | Key Documents Produced or Referenced: Gantt Chart, Milestone Chart, Schedule Data Files | Stakeholders Involved: Project Manager, Scheduler, Team Leads, Sponsor | Dependencies (Previous and Next Processes): Follows Estimate Activity Durations; precedes Control Schedule | Custom Column 1: KPIs or Success Metrics: Schedule baseline approved and shared with stakeholders | Custom Column 2: Risks If Skipped: Project may lack a roadmap, leading to missed deadlines and coordination issues | Custom Column 3: Practical Example or Case: Construction schedule developed using MS Project with resource leveling and float analysis. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Understand critical path and float; always track changes against the baseline. | : | : | :
Planning | Cost Management | Plan Cost Management |  |  |  | Why – Purpose/Need of this process in a project context: To define how project costs will be estimated, budgeted, managed, and controlled. | What – Clear definition of what happens in this process: Establishes the cost management plan that sets the framework for planning, estimating, and controlling costs. | How – Steps involved and techniques used in execution: Meet with finance stakeholders, define methods, units of measure, accuracy levels, and control thresholds. | When – At what stage/time this process is initiated in the lifecycle: Before estimating costs or setting budgets. | Where – Where this process is applied or found: Part of the overall project management plan; referenced in cost tracking systems. | Main Inputs: Project Charter, Project Management Plan, EEFs, OPAs | Main Outputs: Cost Management Plan | Key Tools & Techniques: Expert Judgment, Data Analysis, Meetings | Key Documents Produced or Referenced: Cost Management Plan, Financial Guidelines | Stakeholders Involved: Project Manager, Finance Team, Sponsor | Dependencies (Previous and Next Processes): Follows Project Management Plan; precedes Estimate Costs | Custom Column 1: KPIs or Success Metrics: Cost estimation methods and control procedures clearly documented | Custom Column 2: Risks If Skipped: Cost overruns, lack of financial accountability, poor decision making | Custom Column 3: Practical Example or Case: Agile project defines burn rate, iteration cost, and reporting frequency in cost management plan. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Cost plan must align with organizational finance policies—check EEFs and OPAs. | : | : | :
Planning | Cost Management | Estimate Costs |  |  |  | Why – Purpose/Need of this process in a project context: To develop an approximation of the monetary resources needed to complete project activities. | What – Clear definition of what happens in this process: Cost estimates are developed for all resources including labor, materials, equipment, and services. | How – Steps involved and techniques used in execution: Use techniques like analogous, parametric, bottom-up, and three-point estimating; consider reserves. | When – At what stage/time this process is initiated in the lifecycle: After cost management plan and activity list are ready. | Where – Where this process is applied or found: Used in budgeting, procurement, and performance tracking. | Main Inputs: Cost Management Plan, Project Schedule, Resource Requirements, Risk Register | Main Outputs: Cost Estimates, Basis of Estimates, Project Document Updates | Key Tools & Techniques: Analogous Estimating, Parametric Estimating, Bottom-Up Estimating, Three-Point Estimating, Reserve Analysis | Key Documents Produced or Referenced: Estimate Sheets, Vendor Quotes, Labor Rate Cards | Stakeholders Involved: Project Manager, Estimators, Procurement, SMEs | Dependencies (Previous and Next Processes): Follows Plan Cost Management; precedes Determine Budget | Custom Column 1: KPIs or Success Metrics: Detailed and traceable cost breakdown by activity | Custom Column 2: Risks If Skipped: Underbudgeting, lack of funding, scope delays due to financial shortfalls | Custom Column 3: Practical Example or Case: Estimating construction costs for a hospital using cost per sq. ft. benchmarks and contractor quotes. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Always validate assumptions—cost estimating is closely tied with risk planning. | : | : | :
Planning | Cost Management | Determine Budget |  |  |  | Why – Purpose/Need of this process in a project context: To aggregate the estimated costs of individual activities to establish an authorized cost baseline. | What – Clear definition of what happens in this process: Combines all activity cost estimates to determine a project budget, including contingency and management reserves. | How – Steps involved and techniques used in execution: Aggregate activity estimates, include reserves, analyze funding limits, and baseline the budget. | When – At what stage/time this process is initiated in the lifecycle: After estimating costs and before executing the work. | Where – Where this process is applied or found: Used in financial planning, control processes, and funding requests. | Main Inputs: Cost Estimates, Project Schedule, Risk Register, Agreements, OPAs | Main Outputs: Cost Baseline, Project Funding Requirements | Key Tools & Techniques: Cost Aggregation, Reserve Analysis, Historical Relationships, Funding Limit Reconciliation | Key Documents Produced or Referenced: Budget Plan, Cost Baseline Document | Stakeholders Involved: Project Manager, Finance Controller, Sponsor | Dependencies (Previous and Next Processes): Follows Estimate Costs; precedes Control Costs | Custom Column 1: KPIs or Success Metrics: Cost baseline approved and aligned with project schedule | Custom Column 2: Risks If Skipped: Funding gaps, unmanaged reserves, stakeholder disputes | Custom Column 3: Practical Example or Case: Budgeting a marketing campaign by rolling up ad spend, creative costs, and platform fees. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Include both contingency and management reserves; don’t mix them up. | : | : | :
Planning | Quality Management | Plan Quality Management |  |  |  | Why – Purpose/Need of this process in a project context: To identify quality requirements and standards for the project and deliverables, and to document how compliance will be demonstrated. | What – Clear definition of what happens in this process: Defines the quality approach, standards, metrics, and procedures to ensure the product or service meets stakeholder expectations. | How – Steps involved and techniques used in execution: Use cost-benefit analysis, benchmarking, design of experiments, quality metrics, and meetings to plan quality efforts. | When – At what stage/time this process is initiated in the lifecycle: Early in planning to guide quality-related decisions throughout the project. | Where – Where this process is applied or found: Part of the project management plan and organizational quality systems. | Main Inputs: Project Charter, Project Management Plan, Stakeholder Register, EEFs, OPAs | Main Outputs: Quality Management Plan, Quality Metrics, Project Document Updates | Key Tools & Techniques: Cost-Benefit Analysis, Benchmarking, Design of Experiments, Cost of Quality, Meetings | Key Documents Produced or Referenced: Quality Management Plan, Quality Checklists, Quality Metrics Document | Stakeholders Involved: Project Manager, Quality Manager, Sponsor, Team Members | Dependencies (Previous and Next Processes): Follows other planning processes; precedes Manage Quality | Custom Column 1: KPIs or Success Metrics: Defined quality metrics and compliance measures documented | Custom Column 2: Risks If Skipped: Poor product quality, rework, dissatisfied stakeholders | Custom Column 3: Practical Example or Case: Defining defect tolerance level for a mobile app's crash rate during peak usage. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Understand COQ components: prevention, appraisal, internal and external failure. | : | : | :
Planning | Resource Management | Plan Resource Management |  |  |  | Why – Purpose/Need of this process in a project context: To ensure that human and physical resources are identified, assigned, and managed effectively throughout the project. | What – Clear definition of what happens in this process: Outlines how project resources will be planned, structured, and managed, including roles and responsibilities. | How – Steps involved and techniques used in execution: Conduct meetings, use organizational theory, and analyze roles using RACI or similar matrices. | When – At what stage/time this process is initiated in the lifecycle: Early planning phase, before acquiring or managing resources. | Where – Where this process is applied or found: Included in the Project Management Plan and shared with resource managers. | Main Inputs: Project Charter, Project Management Plan, Resource Requirements, EEFs, OPAs | Main Outputs: Resource Management Plan, Team Charter | Key Tools & Techniques: Organizational Theory, Expert Judgment, Meetings | Key Documents Produced or Referenced: Resource Management Plan, RACI Matrix, Team Charter | Stakeholders Involved: Project Manager, Functional Managers, HR, Team Members | Dependencies (Previous and Next Processes): Follows project initiation and planning; precedes Estimate Activity Resources | Custom Column 1: KPIs or Success Metrics: Clear team roles and resource assignment procedures defined | Custom Column 2: Risks If Skipped: Conflicts, unclear responsibilities, inefficient use of resources | Custom Column 3: Practical Example or Case: Developing a team charter for cross-functional coordination in a product launch project. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Know difference between RACI, RAM, and organizational charts. | : | : | :
Planning | Communications Management | Plan Communications Management |  |  |  | Why – Purpose/Need of this process in a project context: To determine the communication needs of stakeholders and define how information will be distributed and managed. | What – Clear definition of what happens in this process: Defines who needs what information, when they need it, how it will be delivered, and by whom. | How – Steps involved and techniques used in execution: Stakeholder analysis, communication requirements analysis, and use of communication technology tools. | When – At what stage/time this process is initiated in the lifecycle: Planning stage, after stakeholder identification and project charter approval. | Where – Where this process is applied or found: Part of the communications and stakeholder engagement planning activities. | Main Inputs: Project Charter, Project Management Plan, Stakeholder Register, EEFs, OPAs | Main Outputs: Communications Management Plan | Key Tools & Techniques: Communication Requirements Analysis, Communication Technology, Models and Methods, Interpersonal Skills | Key Documents Produced or Referenced: Communications Matrix, Plan Templates, Stakeholder Maps | Stakeholders Involved: Project Manager, Team Members, Stakeholders, Sponsor | Dependencies (Previous and Next Processes): Follows Identify Stakeholders; precedes Manage Communications | Custom Column 1: KPIs or Success Metrics: Communications are timely, targeted, and tracked | Custom Column 2: Risks If Skipped: Miscommunication, stakeholder disengagement, decision delays | Custom Column 3: Practical Example or Case: Weekly status reports and monthly steering committee presentations defined in plan. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Tailor communications style, channel, and frequency to each stakeholder. | : | : | :
Planning | Risk Management | Plan Risk Management |  |  |  | Why – Purpose/Need of this process in a project context: To define how to conduct risk management activities for the project and ensure alignment with risk appetite. | What – Clear definition of what happens in this process: Outlines the methodology, roles, timing, and tools for identifying and analyzing risks. | How – Steps involved and techniques used in execution: Review project complexity, stakeholder tolerance, use risk policies, and conduct planning meetings. | When – At what stage/time this process is initiated in the lifecycle: Early in planning phase before identifying specific risks. | Where – Where this process is applied or found: Forms part of the overall project management plan. | Main Inputs: Project Charter, Project Management Plan, Stakeholder Register, EEFs, OPAs | Main Outputs: Risk Management Plan | Key Tools & Techniques: Expert Judgment, Data Analysis, Meetings | Key Documents Produced or Referenced: Risk Management Plan, Risk Guidelines, Risk Breakdown Structure | Stakeholders Involved: Project Manager, Risk Manager, Sponsor, Team Leads | Dependencies (Previous and Next Processes): Follows Project Management Plan; precedes Identify Risks | Custom Column 1: KPIs or Success Metrics: Plan includes methodology, categories, roles, thresholds | Custom Column 2: Risks If Skipped: Inconsistent risk analysis, missed opportunities, unmanaged threats | Custom Column 3: Practical Example or Case: Plan includes risk probability-impact matrix and categorization for an ERP rollout. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Ensure risk appetite of key stakeholders is reflected in approach. | : | : | :
Planning | Risk Management | Identify Risks |  |  |  | Why – Purpose/Need of this process in a project context: To identify individual project risks and sources of overall project risk, enabling proactive management. | What – Clear definition of what happens in this process: A comprehensive list of risks is developed, including threats and opportunities, along with their characteristics. | How – Steps involved and techniques used in execution: Brainstorming, checklists, SWOT, expert judgment, and root cause analysis are used to identify risks. | When – At what stage/time this process is initiated in the lifecycle: After risk planning and during iterative risk reviews throughout planning and execution. | Where – Where this process is applied or found: Used in the creation and updates of the risk register and risk report. | Main Inputs: Risk Management Plan, Project Documents, Agreements, EEFs, OPAs | Main Outputs: Risk Register, Risk Report, Project Document Updates | Key Tools & Techniques: Interviews, Brainstorming, Checklists, Root Cause Analysis, SWOT, Assumption Analysis | Key Documents Produced or Referenced: Risk Register, Risk Report, Risk Breakdown Structure | Stakeholders Involved: Project Manager, Risk Manager, SMEs, Stakeholders | Dependencies (Previous and Next Processes): Follows Plan Risk Management; precedes Perform Qualitative Risk Analysis | Custom Column 1: KPIs or Success Metrics: Risk register is complete, reviewed, and categorized | Custom Column 2: Risks If Skipped: Unexpected issues, missed mitigation opportunities, stakeholder dissatisfaction | Custom Column 3: Practical Example or Case: Team identifies vendor delay as a key risk during procurement planning for a cloud migration project. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Risks include both threats and opportunities—don’t focus only on negatives. | : | : | :
Planning | Risk Management | Perform Qualitative Risk Analysis |  |  |  | Why – Purpose/Need of this process in a project context: To prioritize individual project risks for further analysis or action by assessing their probability of occurrence and impact. | What – Clear definition of what happens in this process: Risks are evaluated qualitatively based on their likelihood and consequences, and categorized by risk type. | How – Steps involved and techniques used in execution: Use probability-impact matrix, risk categorization, expert judgment, and interviews to rank risks. | When – At what stage/time this process is initiated in the lifecycle: After identifying risks, before quantifying or planning responses. | Where – Where this process is applied or found: Used in developing the risk register and prioritizing mitigation plans. | Main Inputs: Risk Register, Risk Management Plan, Project Documents, EEFs, OPAs | Main Outputs: Project Document Updates (including updated Risk Register) | Key Tools & Techniques: Risk Probability and Impact Assessment, Risk Categorization, Data Representation, Expert Judgment | Key Documents Produced or Referenced: Updated Risk Register with qualitative scores | Stakeholders Involved: Project Manager, Risk Analyst, SMEs, Stakeholders | Dependencies (Previous and Next Processes): Follows Identify Risks; precedes Perform Quantitative Risk Analysis | Custom Column 1: KPIs or Success Metrics: Risks categorized and prioritized by severity | Custom Column 2: Risks If Skipped: Focus on low-priority risks, ineffective response planning | Custom Column 3: Practical Example or Case: High-impact supplier delay risk is escalated based on probability-impact matrix. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Not all projects perform quantitative analysis—this step is typically done in all. | : | : | :
Planning | Risk Management | Perform Quantitative Risk Analysis |  |  |  | Why – Purpose/Need of this process in a project context: To numerically analyze the effect of identified risks on overall project objectives. | What – Clear definition of what happens in this process: Quantifies the impact of risks on project schedule and cost using modeling and simulation techniques. | How – Steps involved and techniques used in execution: Use Monte Carlo simulations, sensitivity analysis, decision tree analysis, and modeling techniques. | When – At what stage/time this process is initiated in the lifecycle: After qualitative risk analysis, if detailed numerical analysis is warranted. | Where – Where this process is applied or found: Used in high-risk or complex projects requiring detailed risk quantification. | Main Inputs: Risk Register, Risk Management Plan, Cost Estimates, Schedule Forecasts | Main Outputs: Project Document Updates (including updated Risk Register and risk report) | Key Tools & Techniques: Simulation, Sensitivity Analysis, Decision Tree, Expert Judgment | Key Documents Produced or Referenced: Risk Report, Monte Carlo Outputs, Tornado Diagrams | Stakeholders Involved: Project Manager, Risk Analyst, Financial Analyst, Sponsor | Dependencies (Previous and Next Processes): Follows Qualitative Risk Analysis; precedes Plan Risk Responses | Custom Column 1: KPIs or Success Metrics: Quantified impact of high-priority risks on cost/schedule | Custom Column 2: Risks If Skipped: Inadequate insight into risk exposure, missed budget/schedule buffers | Custom Column 3: Practical Example or Case: ERP project models cost risk exposure using Monte Carlo to plan contingency reserve. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Only needed for select projects—know when it's optional. | : | : | :
Planning | Risk Management | Plan Risk Responses |  |  |  | Why – Purpose/Need of this process in a project context: To develop options and actions to enhance opportunities and reduce threats to project objectives. | What – Clear definition of what happens in this process: Plans are created for addressing high-priority risks through mitigation, avoidance, transfer, or acceptance. | How – Steps involved and techniques used in execution: Select strategies, assign owners, and develop contingency and fallback plans. | When – At what stage/time this process is initiated in the lifecycle: After risk analysis is complete and before implementing risk-related actions. | Where – Where this process is applied or found: Integrated into overall project plan and risk register updates. | Main Inputs: Risk Register, Risk Management Plan, Project Documents | Main Outputs: Change Requests, Project Document Updates | Key Tools & Techniques: Strategies for Threats/Opportunities, Contingent Response Strategies, Expert Judgment | Key Documents Produced or Referenced: Updated Risk Register, Response Strategy Table | Stakeholders Involved: Project Manager, Risk Owners, Functional Managers | Dependencies (Previous and Next Processes): Follows Perform Quantitative Risk Analysis; precedes Implement Risk Responses | Custom Column 1: KPIs or Success Metrics: Response strategies documented and assigned | Custom Column 2: Risks If Skipped: Reactive risk handling, unassigned risk owners, project surprises | Custom Column 3: Practical Example or Case: Cybersecurity risk assigned to IT lead with a mitigation plan involving backup systems. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Know the difference between risk responses: mitigate, transfer, accept, exploit, enhance, share. | : | : | :
Planning | Procurement Management | Plan Procurement Management |  |  |  | Why – Purpose/Need of this process in a project context: To determine what to procure, how, when, and from whom. | What – Clear definition of what happens in this process: Defines procurement approach, types of contracts, evaluation criteria, and roles/responsibilities. | How – Steps involved and techniques used in execution: Make-or-buy analysis, market research, contract type selection, risk assessments, and procurement strategy definition. | When – At what stage/time this process is initiated in the lifecycle: Early in planning after scope and cost estimation. | Where – Where this process is applied or found: Forms part of the procurement strategy and Project Management Plan. | Main Inputs: Project Charter, Business Documents, Project Schedule, Resource Requirements, Risk Register | Main Outputs: Procurement Management Plan, Procurement Strategy, Bid Documents, Source Selection Criteria, Make-or-Buy Decisions | Key Tools & Techniques: Make-or-Buy Analysis, Expert Judgment, Market Research, Meetings | Key Documents Produced or Referenced: RFPs, RFQs, SOWs, Procurement Strategy Document | Stakeholders Involved: Project Manager, Procurement Manager, Legal, Vendor Manager | Dependencies (Previous and Next Processes): Follows Define Scope and Estimate Costs; precedes Conduct Procurements | Custom Column 1: KPIs or Success Metrics: Sourcing approach defined, compliant bid documents prepared | Custom Column 2: Risks If Skipped: Improper contracts, procurement delays, legal exposure | Custom Column 3: Practical Example or Case: Outsourcing mobile app development with fixed-price contract based on detailed SoW. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Know difference between contract types: FP, T&M, CR; use make-or-buy wisely. | : | : | :
Planning | Stakeholder Management | Plan Stakeholder Engagement |  |  |  | Why – Purpose/Need of this process in a project context: To develop approaches to involve project stakeholders based on their needs, expectations, and potential impact. | What – Clear definition of what happens in this process: Defines strategies and actions for engaging stakeholders effectively throughout the project. | How – Steps involved and techniques used in execution: Analyze stakeholder influence and interest; define engagement strategies and communication modes. | When – At what stage/time this process is initiated in the lifecycle: During planning, after stakeholder identification and communication planning. | Where – Where this process is applied or found: Used in project management plan and stakeholder engagement records. | Main Inputs: Stakeholder Register, Project Charter, Project Management Plan, EEFs, OPAs | Main Outputs: Stakeholder Engagement Plan | Key Tools & Techniques: Stakeholder Analysis, Expert Judgment, Meetings, Data Representation (Grids, Matrices) | Key Documents Produced or Referenced: Stakeholder Engagement Matrix, Power-Interest Grid | Stakeholders Involved: Project Manager, Stakeholders, Sponsor, Communications Lead | Dependencies (Previous and Next Processes): Follows Identify Stakeholders and Plan Communications; precedes Manage Stakeholder Engagement | Custom Column 1: KPIs or Success Metrics: Engagement strategy aligned with stakeholder needs and influence | Custom Column 2: Risks If Skipped: Stakeholder resistance, poor alignment, missed inputs or support | Custom Column 3: Practical Example or Case: Engaging senior execs via monthly strategy briefings, field staff via weekly huddles. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Use engagement assessments to move stakeholders from passive to supportive. | : | : | :
Executing | Integration Management | Direct and Manage Project Work |  |  |  | Why – Purpose/Need of this process in a project context: To lead and perform the work defined in the project management plan and implement approved changes. | What – Clear definition of what happens in this process: All project activities are executed and deliverables are produced based on the plan. | How – Steps involved and techniques used in execution: Coordinate resources, issue work assignments, manage communications, and track deliverable progress. | When – At what stage/time this process is initiated in the lifecycle: At the beginning of project execution and continues throughout. | Where – Where this process is applied or found: Across all executing tasks; central to project delivery. | Main Inputs: Project Management Plan, Approved Change Requests, EEFs, OPAs | Main Outputs: Deliverables, Work Performance Data, Change Requests, Issue Log | Key Tools & Techniques: Expert Judgment, PMIS, Meetings | Key Documents Produced or Referenced: Work Performance Reports, Deliverables, Issue Log | Stakeholders Involved: Project Manager, Project Team, Sponsor, Functional Managers | Dependencies (Previous and Next Processes): Follows planning processes; precedes Monitor and Control Project Work | Custom Column 1: KPIs or Success Metrics: Deliverables completed on time and as per quality standards | Custom Column 2: Risks If Skipped: Work is uncoordinated, unmanaged changes, stakeholder confusion | Custom Column 3: Practical Example or Case: Software team begins development based on sprint plan and manages change requests real-time. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Ensure traceability between plan and execution; log issues as they arise. | : | : | :
Executing | Quality Management | Manage Quality |  |  |  | Why – Purpose/Need of this process in a project context: To ensure that quality processes and standards are being followed and improve performance where needed. | What – Clear definition of what happens in this process: Translates the quality management plan into actionable quality activities using audits and process analysis. | How – Steps involved and techniques used in execution: Conduct quality audits, process analysis, and review results for continuous improvement. | When – At what stage/time this process is initiated in the lifecycle: During project execution after quality planning is complete. | Where – Where this process is applied or found: Throughout production, testing, and quality assurance activities. | Main Inputs: Quality Management Plan, Quality Metrics, Work Performance Data | Main Outputs: Quality Reports, Change Requests, Project Document Updates | Key Tools & Techniques: Data Analysis, Audits, Design for X, Problem Solving | Key Documents Produced or Referenced: Audit Reports, Quality Checklists, Quality Metrics Reports | Stakeholders Involved: Quality Assurance Team, Project Manager, Functional Leads | Dependencies (Previous and Next Processes): Follows Plan Quality Management; precedes Control Quality | Custom Column 1: KPIs or Success Metrics: Number of process non-conformities identified and resolved | Custom Column 2: Risks If Skipped: Uncontrolled quality defects, missed opportunities for improvement | Custom Column 3: Practical Example or Case: Conducting a mid-project process audit to identify gaps in test execution. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Focuses on process (vs. Control Quality which checks deliverables). | : | : | :
Executing | Resource Management | Acquire Resources |  |  |  | Why – Purpose/Need of this process in a project context: To ensure the necessary team members, equipment, and materials are obtained for project execution. | What – Clear definition of what happens in this process: Resources are secured through hiring, purchasing, or internal assignments. | How – Steps involved and techniques used in execution: Negotiate with functional managers, contract vendors, and assign physical resources as needed. | When – At what stage/time this process is initiated in the lifecycle: Before or at the beginning of project execution. | Where – Where this process is applied or found: In staffing plans, procurement records, and team onboarding documents. | Main Inputs: Resource Management Plan, Procurement Documents, Project Schedule | Main Outputs: Physical Resource Assignments, Project Team Assignments, Resource Calendars | Key Tools & Techniques: Negotiation, Pre-assignment, Acquisition, Virtual Teams | Key Documents Produced or Referenced: Assignment Records, Resource Calendars, Staffing Agreements | Stakeholders Involved: Project Manager, Functional Managers, Procurement, HR | Dependencies (Previous and Next Processes): Follows Plan Resource Management; precedes Develop Team | Custom Column 1: KPIs or Success Metrics: Resources available as per project schedule and budget | Custom Column 2: Risks If Skipped: Delays due to lack of staff, wrong skill sets, idle equipment | Custom Column 3: Practical Example or Case: Hiring a testing team and securing test labs for a release cycle. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Includes both team and physical resources—don't confuse with Develop Team. | : | : | :
Executing | Resource Management | Develop Team |  |  |  | Why – Purpose/Need of this process in a project context: To improve competencies, team interaction, and overall team environment to enhance project performance. | What – Clear definition of what happens in this process: Focuses on building team skills, fostering trust, and improving collaboration. | How – Steps involved and techniques used in execution: Conduct team-building activities, individual assessments, training, and use recognition systems. | When – At what stage/time this process is initiated in the lifecycle: During execution once team members are onboarded. | Where – Where this process is applied or found: On internal HR systems, performance plans, and team events. | Main Inputs: Resource Management Plan, Team Charter, Project Schedule | Main Outputs: Team Performance Assessments, Change Requests, Project Document Updates | Key Tools & Techniques: Training, Team-Building, Recognition & Rewards, Colocation, Individual Assessment Tools | Key Documents Produced or Referenced: Training Plans, Assessment Reports, Recognition Logs | Stakeholders Involved: Project Manager, Team Members, Functional Managers | Dependencies (Previous and Next Processes): Follows Acquire Resources; precedes Manage Team | Custom Column 1: KPIs or Success Metrics: Improved team velocity, fewer interpersonal conflicts, high morale | Custom Column 2: Risks If Skipped: Team misalignment, poor productivity, attrition | Custom Column 3: Practical Example or Case: Running agile team retros and recognizing sprint achievements to boost morale. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Distinct from Manage Team—this focuses on development, not supervision. | : | : | :
Executing | Resource Management | Manage Team |  |  |  | Why – Purpose/Need of this process in a project context: To track team performance, provide feedback, resolve issues, and manage changes to optimize project performance. | What – Clear definition of what happens in this process: Daily team coordination, issue resolution, performance tracking, and conflict management occur here. | How – Steps involved and techniques used in execution: Conduct regular performance appraisals, provide feedback, resolve conflicts, and use issue logs. | When – At what stage/time this process is initiated in the lifecycle: Throughout execution after team is formed. | Where – Where this process is applied or found: In status meetings, performance dashboards, HR records. | Main Inputs: Project Management Plan, Work Performance Reports, Team Performance Assessments | Main Outputs: Change Requests, Project Document Updates | Key Tools & Techniques: Conflict Management, Interpersonal Skills, Leadership, Performance Appraisals | Key Documents Produced or Referenced: Issue Logs, Performance Reports, Team Feedback Logs | Stakeholders Involved: Project Manager, Team Members, Functional Managers | Dependencies (Previous and Next Processes): Follows Develop Team; precedes Monitor Team Performance | Custom Column 1: KPIs or Success Metrics: Team issues resolved quickly, performance targets achieved | Custom Column 2: Risks If Skipped: Team dysfunction, unresolved conflicts, poor output | Custom Column 3: Practical Example or Case: Resolving a conflict between QA and Dev teams during release cycle. | Notes/Tips – Common pitfalls, exam traps, or pro tips: This is active management—includes motivation, coaching, and feedback. | : | : | :
Executing | Communications Management | Manage Communications |  |  |  | Why – Purpose/Need of this process in a project context: To ensure timely and appropriate collection, creation, distribution, storage, retrieval, and ultimate disposition of project information. | What – Clear definition of what happens in this process: Implements the communication plan and manages the flow of project information among stakeholders. | How – Steps involved and techniques used in execution: Create reports, hold meetings, use collaboration tools, and maintain communication logs. | When – At what stage/time this process is initiated in the lifecycle: Throughout the executing phase after communication planning. | Where – Where this process is applied or found: Across team platforms, dashboards, emails, and stakeholder meetings. | Main Inputs: Project Communications, Project Management Plan, Work Performance Reports, EEFs, OPAs | Main Outputs: Project Communications, Project Document Updates | Key Tools & Techniques: Communication Technology, Communication Methods, Interpersonal and Team Skills, PMIS | Key Documents Produced or Referenced: Status Reports, Dashboards, Meeting Minutes | Stakeholders Involved: Project Manager, Project Team, Stakeholders, Sponsor | Dependencies (Previous and Next Processes): Follows Plan Communications Management; precedes Monitor Communications | Custom Column 1: KPIs or Success Metrics: Stakeholders receive timely and relevant updates | Custom Column 2: Risks If Skipped: Lack of visibility, missed feedback, misaligned expectations | Custom Column 3: Practical Example or Case: Weekly dashboard emailed to leadership and posted on project portal. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Tailor format and frequency to each audience; track delivery and understanding. | : | : | :
Executing | Risk Management | Implement Risk Responses |  |  |  | Why – Purpose/Need of this process in a project context: To implement agreed-upon risk response plans and monitor their effectiveness. | What – Clear definition of what happens in this process: Executes planned risk responses by engaging owners and applying mitigation or enhancement actions. | How – Steps involved and techniques used in execution: Delegate responsibilities, track execution of contingency plans, and review effectiveness. | When – At what stage/time this process is initiated in the lifecycle: During execution after Plan Risk Responses is approved. | Where – Where this process is applied or found: Within execution tasks, issue logs, and stakeholder reports. | Main Inputs: Risk Register, Risk Report, Project Management Plan | Main Outputs: Change Requests, Project Document Updates | Key Tools & Techniques: Expert Judgment, Project Management Information System (PMIS), Interpersonal Skills | Key Documents Produced or Referenced: Risk Logs, Action Trackers, Lessons Learned | Stakeholders Involved: Project Manager, Risk Owners, Team Members | Dependencies (Previous and Next Processes): Follows Plan Risk Responses; precedes Monitor Risks | Custom Column 1: KPIs or Success Metrics: Risk responses executed as planned with documented outcomes | Custom Column 2: Risks If Skipped: Risks materialize unchecked, reduced team confidence, lost time | Custom Column 3: Practical Example or Case: Risk owner activates alternate supplier when primary vendor fails to deliver. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Ensure owners know and accept responsibilities—don’t just assign. | : | : | :
Executing | Procurement Management | Conduct Procurements |  |  |  | Why – Purpose/Need of this process in a project context: To obtain seller responses, select a seller, and award a contract. | What – Clear definition of what happens in this process: The procurement process is executed—bids are received, evaluated, negotiated, and awarded. | How – Steps involved and techniques used in execution: Send RFQs, hold bidder conferences, evaluate proposals, negotiate and finalize contracts. | When – At what stage/time this process is initiated in the lifecycle: After procurement planning and before work execution with external vendors. | Where – Where this process is applied or found: Within procurement teams, legal review, and contract repositories. | Main Inputs: Procurement Management Plan, Bid Documents, Seller Proposals, Procurement Statement of Work | Main Outputs: Selected Sellers, Agreements, Change Requests | Key Tools & Techniques: Bidder Conferences, Proposal Evaluation Techniques, Negotiation, Interpersonal Skills | Key Documents Produced or Referenced: Contracts, Evaluation Scorecards, Procurement Agreements | Stakeholders Involved: Project Manager, Procurement Manager, Legal, Sellers | Dependencies (Previous and Next Processes): Follows Plan Procurement Management; precedes Control Procurements | Custom Column 1: KPIs or Success Metrics: Vendors selected per criteria and contracts executed on time | Custom Column 2: Risks If Skipped: Unclear vendor obligations, delays in delivery, legal risks | Custom Column 3: Practical Example or Case: Awarding website hosting contract based on best technical and cost score. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Understand contract types and evaluation methods; document negotiation outcomes. | : | : | :
Executing | Stakeholder Management | Manage Stakeholder Engagement |  |  |  | Why – Purpose/Need of this process in a project context: To communicate and work with stakeholders to meet their needs and expectations, address issues, and foster engagement. | What – Clear definition of what happens in this process: Uses strategies to keep stakeholders engaged and committed through communication, conflict resolution, and feedback loops. | How – Steps involved and techniques used in execution: Hold regular touchpoints, manage concerns, adjust engagement strategies. | When – At what stage/time this process is initiated in the lifecycle: During execution after planning stakeholder engagement. | Where – Where this process is applied or found: In stakeholder logs, communications records, project reviews. | Main Inputs: Stakeholder Engagement Plan, Project Management Plan, Change Log | Main Outputs: Change Requests, Issue Log Updates, Project Document Updates | Key Tools & Techniques: Interpersonal Skills, Communication Methods, Conflict Management, Observation | Key Documents Produced or Referenced: Engagement Logs, Feedback Summaries, Stakeholder Reports | Stakeholders Involved: Project Manager, Stakeholders, Team Members, Sponsor | Dependencies (Previous and Next Processes): Follows Plan Stakeholder Engagement; precedes Monitor Stakeholder Engagement | Custom Column 1: KPIs or Success Metrics: Stakeholder satisfaction score, positive sentiment, issue resolution rate | Custom Column 2: Risks If Skipped: Resistance, surprise escalations, loss of trust | Custom Column 3: Practical Example or Case: Engaging local community leaders weekly during infrastructure rollout to reduce opposition. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Not just about updates—emphasize two-way communication and responsiveness. | : | : | :
Monitoring and Controlling | Integration Management | Monitor and Control Project Work |  |  |  | Why – Purpose/Need of this process in a project context: To track, review, and regulate progress toward project objectives and performance targets. | What – Clear definition of what happens in this process: Actual performance is compared against the project plan and corrective actions are identified. | How – Steps involved and techniques used in execution: Analyze work performance data, forecast future performance, recommend changes. | When – At what stage/time this process is initiated in the lifecycle: Throughout the project lifecycle from execution onward. | Where – Where this process is applied or found: Dashboards, performance reports, control charts, trend analysis. | Main Inputs: Project Management Plan, Work Performance Information, EEFs, OPAs | Main Outputs: Work Performance Reports, Change Requests, Project Document Updates | Key Tools & Techniques: Expert Judgment, Data Analysis, Decision Making, Meetings | Key Documents Produced or Referenced: Performance Reports, Variance Analysis, Trend Forecasts | Stakeholders Involved: Project Manager, Sponsor, PMO, Team Leads | Dependencies (Previous and Next Processes): Follows Direct and Manage Project Work; precedes Integrated Change Control | Custom Column 1: KPIs or Success Metrics: Deviation from baseline within acceptable thresholds | Custom Column 2: Risks If Skipped: Undetected problems, performance drift, budget/schedule overruns | Custom Column 3: Practical Example or Case: Tracking earned value metrics weekly to adjust resource allocation in a manufacturing project. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Know difference between Work Performance Data, Information, and Reports. | : | : | :
Monitoring and Controlling | Integration Management | Perform Integrated Change Control |  |  |  | Why – Purpose/Need of this process in a project context: To review, approve, and manage all change requests in a coordinated way. | What – Clear definition of what happens in this process: Evaluates change requests and ensures only approved changes are implemented while maintaining project integrity. | How – Steps involved and techniques used in execution: Use change control board (CCB), perform impact analysis, communicate decisions, and update baselines. | When – At what stage/time this process is initiated in the lifecycle: Throughout the project once execution begins. | Where – Where this process is applied or found: In change logs, updated plans, and CCB records. | Main Inputs: Project Management Plan, Work Performance Reports, Change Requests | Main Outputs: Approved Change Requests, Change Log, Updates to Project Documents | Key Tools & Techniques: Expert Judgment, Change Control Tools, Decision Making, Meetings | Key Documents Produced or Referenced: Change Log, Updated Plans, Approval Records | Stakeholders Involved: Project Manager, Change Control Board (CCB), Sponsor, Team Leads | Dependencies (Previous and Next Processes): Follows Monitor & Control Project Work; precedes Direct Work changes and Updates | Custom Column 1: KPIs or Success Metrics: Percentage of change requests processed within SLA; change success rate | Custom Column 2: Risks If Skipped: Uncontrolled changes, project drift, stakeholder conflict | Custom Column 3: Practical Example or Case: CCB reviews scope change to add new features and approves after resource check. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Know the change request lifecycle; CCB decisions are final and must be documented. | : | : | :
Monitoring and Controlling | Scope Management | Validate Scope |  |  |  | Why – Purpose/Need of this process in a project context: To formalize the acceptance of the completed project deliverables by the customer or sponsor. | What – Clear definition of what happens in this process: The customer reviews deliverables and either accepts them or requests revisions. | How – Steps involved and techniques used in execution: Use inspection, walkthroughs, and review sessions to validate deliverables against scope. | When – At what stage/time this process is initiated in the lifecycle: After deliverables are created and before closing or transitioning work. | Where – Where this process is applied or found: In client-facing documents, signed-off deliverables, and acceptance logs. | Main Inputs: Project Management Plan, Verified Deliverables, Requirements Documentation | Main Outputs: Accepted Deliverables, Change Requests, Work Performance Information | Key Tools & Techniques: Inspection, Decision Making, Reviews | Key Documents Produced or Referenced: Sign-off Sheets, Acceptance Logs, Deliverable Checklists | Stakeholders Involved: Project Manager, Sponsor, Customer, Quality Team | Dependencies (Previous and Next Processes): Follows Control Quality; precedes Close Project | Custom Column 1: KPIs or Success Metrics: Percentage of deliverables formally accepted without rework | Custom Column 2: Risks If Skipped: Client dissatisfaction, misalignment with expectations, scope disputes | Custom Column 3: Practical Example or Case: Client signs off on wireframes after validating them against initial requirements. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Don’t confuse with Control Quality—this is customer validation, not internal QC. | : | : | :
Monitoring and Controlling | Scope Management | Control Scope |  |  |  | Why – Purpose/Need of this process in a project context: To monitor project and product scope and manage changes to the scope baseline. | What – Clear definition of what happens in this process: Ensures that all requested changes to scope go through proper approval and that unauthorized scope changes are avoided. | How – Steps involved and techniques used in execution: Compare actual work to scope baseline, log and evaluate scope changes, enforce change control procedures. | When – At what stage/time this process is initiated in the lifecycle: After scope is baselined and continues through project execution. | Where – Where this process is applied or found: In the scope baseline, change log, and work performance data. | Main Inputs: Project Management Plan, Requirements Documentation, Work Performance Data | Main Outputs: Work Performance Information, Change Requests, Project Document Updates | Key Tools & Techniques: Variance Analysis, Trend Analysis, Change Control Tools | Key Documents Produced or Referenced: Scope Baseline, Change Log, Requirements Traceability Matrix | Stakeholders Involved: Project Manager, PMO, Sponsor, Functional Leads | Dependencies (Previous and Next Processes): Follows Validate Scope; loops with Perform Integrated Change Control | Custom Column 1: KPIs or Success Metrics: Number of unauthorized changes prevented; % of approved scope change requests | Custom Column 2: Risks If Skipped: Scope creep, budget overruns, unclear deliverable boundaries | Custom Column 3: Practical Example or Case: Preventing unapproved UI feature requests from bypassing the CCB. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Scope creep is common—control through documented process only. | : | : | :
Monitoring and Controlling | Schedule Management | Control Schedule |  |  |  | Why – Purpose/Need of this process in a project context: To monitor the status of project schedule and manage changes to the schedule baseline. | What – Clear definition of what happens in this process: Tracks progress, identifies deviations, and takes corrective actions to ensure timely completion. | How – Steps involved and techniques used in execution: Compare actual progress to baseline, use forecasting tools, apply schedule compression if needed. | When – At what stage/time this process is initiated in the lifecycle: After schedule is baselined and during ongoing execution. | Where – Where this process is applied or found: Gantt charts, project dashboards, schedule variance reports. | Main Inputs: Project Management Plan, Project Schedule, Work Performance Data | Main Outputs: Schedule Forecasts, Change Requests, Project Document Updates | Key Tools & Techniques: Critical Path Method, Performance Reviews, Forecasting, Trend Analysis | Key Documents Produced or Referenced: Schedule Baseline, Variance Reports, Forecast Logs | Stakeholders Involved: Project Manager, Scheduler, Sponsor, Functional Leads | Dependencies (Previous and Next Processes): Follows Develop Schedule; interacts with Change Control | Custom Column 1: KPIs or Success Metrics: SPI (Schedule Performance Index), variance from planned finish dates | Custom Column 2: Risks If Skipped: Delayed delivery, resource conflicts, missed milestones | Custom Column 3: Practical Example or Case: Identifying slippage in a software release timeline and applying fast tracking to recover. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Know how SPI and EVM tools tie into schedule control. | : | : | :
Monitoring and Controlling | Cost Management | Control Costs |  |  |  | Why – Purpose/Need of this process in a project context: To monitor project cost status and manage changes to the cost baseline. | What – Clear definition of what happens in this process: Compares actual spending with budget and takes corrective actions to control variances. | How – Steps involved and techniques used in execution: Use earned value management, forecasting, and cost trend analysis to identify variances. | When – At what stage/time this process is initiated in the lifecycle: After cost baseline is created; monitored continuously through execution. | Where – Where this process is applied or found: Cost reports, EVM charts, financial dashboards, budget logs. | Main Inputs: Project Management Plan, Project Funding Requirements, Work Performance Data | Main Outputs: Cost Forecasts, Change Requests, Work Performance Information | Key Tools & Techniques: Earned Value Management, Forecasting, TCPI, To-Complete Performance Index | Key Documents Produced or Referenced: Cost Reports, EVM Graphs, Budget Variance Logs | Stakeholders Involved: Project Manager, Sponsor, Finance Controller, PMO | Dependencies (Previous and Next Processes): Follows Determine Budget; loops with Perform Integrated Change Control | Custom Column 1: KPIs or Success Metrics: CPI (Cost Performance Index), Estimate at Completion (EAC) accuracy | Custom Column 2: Risks If Skipped: Overruns, funding shortfalls, uncontrolled burn rate | Custom Column 3: Practical Example or Case: Tracking CPI and EAC on infrastructure rollout to avoid budget overrun. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Know how to interpret EVM values like CPI, SPI, EAC, VAC. | : | : | :
Monitoring and Controlling | Quality Management | Control Quality |  |  |  | Why – Purpose/Need of this process in a project context: To ensure that project outputs meet quality requirements and to identify causes of poor process or product quality. | What – Clear definition of what happens in this process: Verifies deliverables against quality requirements using testing, inspection, and measurement. | How – Steps involved and techniques used in execution: Conduct quality control measurements, inspect outputs, document nonconformities, and recommend corrective actions. | When – At what stage/time this process is initiated in the lifecycle: Performed during the execution and monitoring phases after deliverables are produced. | Where – Where this process is applied or found: Quality logs, testing records, defect reports, and inspection documents. | Main Inputs: Project Management Plan, Quality Metrics, Deliverables, Work Performance Data | Main Outputs: Quality Control Measurements, Verified Deliverables, Change Requests | Key Tools & Techniques: Inspection, Control Charts, Statistical Sampling, Checklist, Testing | Key Documents Produced or Referenced: Defect Logs, Inspection Reports, Test Results | Stakeholders Involved: Quality Control Team, Project Manager, Sponsor | Dependencies (Previous and Next Processes): Follows Manage Quality; precedes Validate Scope | Custom Column 1: KPIs or Success Metrics: Defect density, % of deliverables meeting acceptance criteria | Custom Column 2: Risks If Skipped: Defective outputs, costly rework, stakeholder dissatisfaction | Custom Column 3: Practical Example or Case: Conducting integration testing for a software module and logging defects for resolution. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Don’t confuse with Manage Quality—this checks outputs, not processes. | : | : | :
Monitoring and Controlling | Resource Management | Control Resources |  |  |  | Why – Purpose/Need of this process in a project context: To ensure that physical and team resources are used as planned and to address resource-related issues. | What – Clear definition of what happens in this process: Monitors resource usage, resolves issues, and ensures availability of resources per plan. | How – Steps involved and techniques used in execution: Compare resource assignments vs. actual usage, resolve conflicts, and optimize resource utilization. | When – At what stage/time this process is initiated in the lifecycle: During execution and monitoring after resources are acquired. | Where – Where this process is applied or found: In resource dashboards, usage logs, team calendars, and issue logs. | Main Inputs: Project Management Plan, Resource Assignments, Work Performance Data | Main Outputs: Work Performance Information, Change Requests, Project Document Updates | Key Tools & Techniques: Problem Solving, Negotiation, Interpersonal Skills, PMIS | Key Documents Produced or Referenced: Resource Logs, Conflict Logs, Performance Dashboards | Stakeholders Involved: Project Manager, Team Leads, Functional Managers | Dependencies (Previous and Next Processes): Follows Manage Team; loops with Control Schedule and Cost | Custom Column 1: KPIs or Success Metrics: Resource utilization %, conflict resolution time, availability as per schedule | Custom Column 2: Risks If Skipped: Under/over-utilization, bottlenecks, resource burnout | Custom Column 3: Practical Example or Case: Reallocating development resources when a feature delay causes schedule overlap. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Focuses on availability and optimization—not team motivation or development. | : | : | :
Monitoring and Controlling | Communications Management | Monitor Communications |  |  |  | Why – Purpose/Need of this process in a project context: To ensure stakeholder communication needs are met effectively and efficiently. | What – Clear definition of what happens in this process: Reviews and evaluates communication deliverables and channels for effectiveness and improvements. | How – Steps involved and techniques used in execution: Conduct surveys, review reports, track communication KPIs, and adjust strategy if needed. | When – At what stage/time this process is initiated in the lifecycle: Throughout project monitoring after communication is managed. | Where – Where this process is applied or found: In stakeholder feedback logs, communication audits, and performance reviews. | Main Inputs: Project Management Plan, Project Communications, Work Performance Data | Main Outputs: Work Performance Information, Change Requests, Project Document Updates | Key Tools & Techniques: Communication Technology, Feedback Analysis, Meetings, Expert Judgment | Key Documents Produced or Referenced: Survey Results, Audit Reports, Communication Logs | Stakeholders Involved: Project Manager, Stakeholders, PMO, Communications Lead | Dependencies (Previous and Next Processes): Follows Manage Communications; loops with Manage Stakeholder Engagement | Custom Column 1: KPIs or Success Metrics: Stakeholder communication satisfaction, response time, delivery success rate | Custom Column 2: Risks If Skipped: Information gaps, delays in decision-making, disengagement | Custom Column 3: Practical Example or Case: Conducting a post-launch survey to assess executive satisfaction with updates. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Different from Manage Communications—this evaluates outcomes, not distribution. | : | : | :
Monitoring and Controlling | Risk Management | Monitor Risks |  |  |  | Why – Purpose/Need of this process in a project context: To track identified risks, monitor residual risks, identify new risks, and evaluate risk process effectiveness. | What – Clear definition of what happens in this process: Ensures risks are actively monitored and response plans are implemented and adjusted as needed. | How – Steps involved and techniques used in execution: Conduct risk reviews, reassessments, audits, and track KPIs on mitigation effectiveness. | When – At what stage/time this process is initiated in the lifecycle: Continuously throughout the project lifecycle after implementation starts. | Where – Where this process is applied or found: Risk registers, dashboards, audit logs, lessons learned. | Main Inputs: Risk Management Plan, Risk Register, Work Performance Data | Main Outputs: Work Performance Information, Change Requests, Risk Register Updates | Key Tools & Techniques: Risk Audits, Technical Performance Measurement, Risk Reassessment, Meetings | Key Documents Produced or Referenced: Updated Risk Register, Risk Reports, Risk Audit Logs | Stakeholders Involved: Project Manager, Risk Owners, PMO, Team Leads | Dependencies (Previous and Next Processes): Follows Implement Risk Responses; loops with Plan and Identify Risks | Custom Column 1: KPIs or Success Metrics: Mitigation actions completed, residual risk exposure tracked, emerging risks identified | Custom Column 2: Risks If Skipped: Unmanaged threats, outdated risk responses, unknown exposures | Custom Column 3: Practical Example or Case: Risk audit uncovers a recurring vendor delay not previously logged or mitigated. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Risk monitoring is iterative—plan to update frequently and reassess. | : | : | :
Monitoring and Controlling | Procurement Management | Control Procurements |  |  |  | Why – Purpose/Need of this process in a project context: To ensure that procurement relationships are managed and performance is monitored for compliance. | What – Clear definition of what happens in this process: Tracks contract execution, ensures deliverables meet requirements, and manages vendor-related changes. | How – Steps involved and techniques used in execution: Use procurement audits, performance reviews, and inspections to manage vendor compliance and payments. | When – At what stage/time this process is initiated in the lifecycle: After contract is awarded and throughout execution until final closure. | Where – Where this process is applied or found: In contract dashboards, procurement logs, and invoice systems. | Main Inputs: Procurement Management Plan, Agreements, Work Performance Data | Main Outputs: Work Performance Information, Change Requests, Closed Procurements | Key Tools & Techniques: Claims Administration, Inspections, Audits, Performance Reviews | Key Documents Produced or Referenced: Contract Documents, Inspection Reports, Invoice Logs | Stakeholders Involved: Project Manager, Procurement Manager, Vendor, Legal | Dependencies (Previous and Next Processes): Follows Conduct Procurements; precedes Close Project or Phase | Custom Column 1: KPIs or Success Metrics: Vendor compliance score, timely payments, contract change turnaround | Custom Column 2: Risks If Skipped: Vendor noncompliance, untracked delivery delays, payment disputes | Custom Column 3: Practical Example or Case: Quarterly review of SaaS vendor showing SLA breaches and triggering penalty clause. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Document every step of procurement monitoring—it's legally binding. | : | : | :
Monitoring and Controlling | Stakeholder Management | Monitor Stakeholder Engagement |  |  |  | Why – Purpose/Need of this process in a project context: To ensure stakeholders are appropriately engaged throughout the project lifecycle. | What – Clear definition of what happens in this process: Tracks stakeholder engagement strategies, feedback, and adapts plans to maintain positive relationships. | How – Steps involved and techniques used in execution: Review engagement metrics, solicit feedback, adjust communication and engagement strategies. | When – At what stage/time this process is initiated in the lifecycle: Throughout the execution and monitoring phases. | Where – Where this process is applied or found: Engagement logs, communication reports, feedback surveys. | Main Inputs: Project Management Plan, Stakeholder Engagement Plan, Work Performance Data | Main Outputs: Work Performance Information, Change Requests, Project Document Updates | Key Tools & Techniques: Feedback Analysis, Observation, Expert Judgment, Communication Methods | Key Documents Produced or Referenced: Engagement Reports, Meeting Notes, Feedback Forms | Stakeholders Involved: Project Manager, Stakeholders, Communications Lead, Sponsor | Dependencies (Previous and Next Processes): Follows Manage Stakeholder Engagement; feeds back into planning processes | Custom Column 1: KPIs or Success Metrics: Stakeholder sentiment trends, issue resolution rate, participation rate | Custom Column 2: Risks If Skipped: Stakeholder disengagement, negative impact on project buy-in, increased resistance | Custom Column 3: Practical Example or Case: Adjusting engagement plan after stakeholder survey shows confusion over project scope. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Continuously monitor and adapt—engagement is not one-time activity. | : | : | :
Closing | Integration Management | Close Project or Phase |  |  |  | Why – Purpose/Need of this process in a project context: To finalize all activities, close out contracts, and formally complete the project or a phase. | What – Clear definition of what happens in this process: Ensures all work is complete, deliverables are accepted, documentation is finalized, and lessons are captured. | How – Steps involved and techniques used in execution: Conduct final reviews, obtain formal acceptance, archive documents, release resources, and perform lessons learned sessions. | When – At what stage/time this process is initiated in the lifecycle: Once all deliverables are accepted and no further work remains. | Where – Where this process is applied or found: In closing reports, project repositories, knowledge management systems. | Main Inputs: Project Charter, Project Management Plan, Accepted Deliverables, Agreements | Main Outputs: Final Product/Service/Result Transition, Final Report, Lessons Learned Register | Key Tools & Techniques: Expert Judgment, Data Analysis, Meetings | Key Documents Produced or Referenced: Closure Report, Lessons Learned, Final Acceptance Records | Stakeholders Involved: Project Manager, Sponsor, Customer, PMO | Dependencies (Previous and Next Processes): Follows Validate Scope and Control Procurements; last process in the lifecycle | Custom Column 1: KPIs or Success Metrics: Formal sign-off received, knowledge artifacts archived, resources released on time | Custom Column 2: Risks If Skipped: Legal exposure, untracked lessons, unresolved issues | Custom Column 3: Practical Example or Case: After deployment, final report delivered to client with sign-off and resource release emails sent. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Don’t forget formal acceptance and archiving; lessons learned are critical for future projects. | : | : | :
Closing | Procurement Management | Close Procurements |  |  |  | Why – Purpose/Need of this process in a project context: To complete and settle each contract, including resolving open items and archiving procurement records. | What – Clear definition of what happens in this process: Ensures that all procurement requirements have been met or waived and all agreements are formally closed. | How – Steps involved and techniques used in execution: Review contract terms, confirm deliverable completion, resolve claims, obtain formal acceptance. | When – At what stage/time this process is initiated in the lifecycle: During or after project closure once all vendor deliverables are completed. | Where – Where this process is applied or found: In contract files, vendor performance reports, closure reports. | Main Inputs: Procurement Documentation, Agreements, Procurement Management Plan | Main Outputs: Closed Procurements, Lessons Learned Register, Final Deliverables | Key Tools & Techniques: Audits, Negotiation, Procurement Reviews, Record Management | Key Documents Produced or Referenced: Contract Closure Report, Final Invoices, Release Letters | Stakeholders Involved: Project Manager, Procurement Manager, Legal, Vendor | Dependencies (Previous and Next Processes): Follows Control Procurements; often done along with project closure | Custom Column 1: KPIs or Success Metrics: All contracts closed with zero pending claims, closure documentation archived | Custom Column 2: Risks If Skipped: Ongoing liabilities, payment disputes, compliance issues | Custom Column 3: Practical Example or Case: Final invoice cleared and vendor signed off on data center installation project. | Notes/Tips – Common pitfalls, exam traps, or pro tips: Ensure procurement closure happens even for canceled contracts. | : | : | :
Closing | Quality Management | Finalize Quality Reports |  |  |  | Why – Purpose/Need of this process in a project context: To document the quality performance of the project and capture improvements for future use. | What – Clear definition of what happens in this process: Compiles final quality metrics, audit findings, and process improvement recommendations. | How – Steps involved and techniques used in execution: Review all quality logs and control charts, summarize lessons, and archive with project documentation. | When – At what stage/time this process is initiated in the lifecycle: At project closure or after last deliverable is validated. | Where – Where this process is applied or found: Quality management system, project records, audit summaries. | Main Inputs: Quality Management Plan, Control Quality Outputs, Quality Metrics | Main Outputs: Final Quality Report, Lessons Learned Inputs, Process Improvement Plan | Key Tools & Techniques: Data Analysis, Expert Judgment, Audits | Key Documents Produced or Referenced: Final Quality Report, Audit Findings, Process Logs | Stakeholders Involved: Quality Manager, Project Manager, PMO | Dependencies (Previous and Next Processes): Follows Control Quality and Manage Quality; part of overall closure | Custom Column 1: KPIs or Success Metrics: All quality issues resolved, final audit closed, report submitted to PMO | Custom Column 2: Risks If Skipped: Missed process improvements, repeated mistakes, undocumented defects | Custom Column 3: Practical Example or Case: PMO reviews final quality report to update internal standards for defect handling. | Notes/Tips – Common pitfalls, exam traps, or pro tips: This is not in PMBOK as a separate process but often included in real-world closure documentation. | : | : | :
Project charter | [5 empty] | Project Title and Description (What is the project?) | Project Manager Assigned and Authority Level (Who is given authority to lead the project, and can they determine, manage, and approve changes to budget, schedule, staffing, etc.?) | Business Case (Why is the project being done? On what financial or other basis can we justify doing this project?) | Resources Preassigned (How many or which resources will be provided?) | Key Stakeholder List (Who will affect or be affected by the project [influence the project], as known to date?) | Stakeholder Requirements as Known (Requirements related to both project and product scope.) | High Level Product Description / Key Deliverables (What are the key product deliverables that are wanted and what will be the end result of the project?) | High-Level Assumptions (What is believed to be true or reliable in the situation? What do we believe to be the case but do not have proof or data for?) | High-Level Constraints (What factors may limit our ability to deliver? What boundaries or parameters will the project have to function within?) | Measurable Project Objectives (How does the project tie into the organization's strategic goals? What project objectives support those goals? The objectives need to be measurable and will depend on the defined priority of the project constraints.) | Project Approval Requirements (What items need to be approved for the project, and who will have sign-off authority? What designates success?) | Overall Project Risks (Overall potential threats and opportunities for the project) | Project Exit Criteria (What needs must be met so that the project manager will be able to close or terminate the project or phase?) | Project Sponsors Authorizing This Project (—)
Project Management Plan | [5 empty] | Integration Management Plan (How will the project be integrated and managed holistically?) | Scope Management Plan (How will scope be defined, validated, and controlled?) | Schedule Management Plan (How will the schedule be developed, managed, and controlled?) | Cost Management Plan (How will project costs be estimated, budgeted, and controlled?) | Quality Management Plan (How will quality requirements be met and controlled?) | Resource Management Plan (How will team and physical resources be acquired, developed, and managed?) | Communications Management Plan (How will internal and external communication be handled?) | Risk Management Plan (How will risks be identified, analyzed, and managed?) | Procurement Management Plan (How will goods and services be acquired from outside the project team?) | Stakeholder Engagement Plan (How will stakeholders be engaged and managed?) | Change Management Plan (How will change requests be managed and documented?) | Configuration Management Plan (How will the product and documentation be version-controlled?) | Performance Measurement Baselines (What are the baselines for scope, schedule, and cost?) | Project Life Cycle Description (What phases will the project go through?) | Development Approach (Will you use predictive, agile, hybrid, etc.?) | Tailoring Approach (What customizations were made to standard processes or tools?) | Management Reviews (What reviews are planned and when?)
Outputs | [5 empty] | Project Charter (Formal authorization of the project; includes high-level scope, objectives, and stakeholders) | Project Management Plan (The integrated document describing how the project will be executed, monitored, and closed) | Deliverables (Tangible or intangible products produced as a result of the project work) | Work Performance Data (Raw observations and measurements identified during activities being performed) | Work Performance Information (Performance data analyzed in context to generate actionable information) | Work Performance Reports (Compiled status and progress information for stakeholder communication) | Change Requests (Formal proposals to modify any project document, deliverable, or baseline) | Approved Change Requests (Changes formally reviewed and approved for implementation) | Issue Log (Documented list of issues and their resolution tracking throughout the project) | Lessons Learned Register (Captures knowledge gained and records it for future use) | Risk Register (Details identified risks, their characteristics, and responses) | Risk Report (Summarized information about overall and individual project risks) | Quality Reports (Output of quality control activities including compliance status and improvement recommendations) | Test and Evaluation Documents (Documents for validating project deliverables and outcomes) | Team Performance Assessments (Evaluation of team effectiveness and areas for improvement) | Resource Calendars (Availability of project resources over time) | Stakeholder Register (Identifies project stakeholders, their interests, influence, and communication needs) | Procurement Statement of Work (Describes goods/services to be procured in detail) | Agreements / Contracts (Formal documents between buyer and seller outlining terms and conditions) | Final Product, Service, or Result Transition (Formal handover to operations or customer) | Final Report (Summary of project performance, results achieved, and lessons learned) | Accepted Deliverables (Deliverables formally signed off by the customer or sponsor) | Requirements Traceability Matrix (Links requirements to their origin and tracks throughout the project lifecycle) | Project Schedule (Detailed timeline of activities, milestones, and resources) | Project Budget (Authorized cost baseline for the project work) | Milestone List (Key project milestones with target dates)
RAID register | Risk |  |  |  |  | Risk ID: Unique identifier for the risk ¦ Example: R-001 | Risk Description: What could go wrong that may affect the project ¦ Example: Server outage may affect user access | Impact: Consequences if the risk occurs ¦ Example: Project delayed by 3 days | Likelihood: Probability of the risk occurring ¦ Example: High (80%) | Severity: Overall seriousness of the risk ¦ Example: Critical | Owner: Person responsible for managing the risk ¦ Example: IT Infrastructure Lead | Mitigation Plan: Actions to reduce likelihood or impact ¦ Example: Add backup server in another region | Contingency Plan: Backup plan if risk materializes ¦ Example: Switch to cloud provider temporarily | Status: Current state of the risk ¦ Example: Open
RAID register | Assumptions |  |  |  |  | Assumption ID: Unique identifier for the assumption ¦ Example: A-002 | Assumption Statement: Belief accepted as true without proof, used for planning ¦ Example: Vendor will deliver API by June 1 | Impact if False: Effect if assumption turns out invalid ¦ Example: Integration delayed by 2 weeks | Owner: Person validating or tracking this assumption ¦ Example: Project Manager | Validation Plan: How this assumption will be verified ¦ Example: Check-in with vendor by May 15 | Status: Current state of the assumption ¦ Example: Validated
RAID register | Issues |  |  |  |  | Issue ID: Unique identifier for the issue ¦ Example: I-005 | Issue Description: A problem affecting the project right now ¦ Example: Payment gateway integration fails | Impact: Effect on cost, timeline, or quality ¦ Example: UAT testing blocked | Severity: Priority or seriousness ¦ Example: High | Date Identified: Date issue was logged ¦ Example: 2025-04-15 | Owner: Assigned person to resolve it ¦ Example: Backend Developer | Resolution Plan: Steps to resolve the issue ¦ Example: Update credentials, reconfigure API headers | Target Resolution Date: Expected date of resolution ¦ Example: 2025-04-20 | Status: Current status of the issue ¦ Example: In Progress
RAID register | Dependencies |  |  |  |  | Dependency ID: Unique identifier for the dependency ¦ Example: D-003 | Dependency Description: Description of the dependent task or input ¦ Example: Client must approve wireframes before dev starts | Type: Nature of dependency ¦ Example: External | Owner: Person responsible for delivery or coordination ¦ Example: UX Lead | Impact if Delayed: Effect if delivery is late ¦ Example: Design team blocked, sprint delayed | Due Date: Deadline for resolving the dependency ¦ Example: 2025-04-25 | Status: Current progress status ¦ Example: Not Started | Follow-up Actions: Monitoring or escalation actions ¦ Example: Follow up via email every 2 days until signed off

## Sheet5
¦ Process Group ¦ Knowledge Area ¦ Process ¦ Dependent Processes ¦ Custom Column 1 ¦ Custom Column 2 ¦ Purpose ¦ Main Output ¦ Key Elements ¦ Inputs ¦ Tools & Techniques ¦ Notes ¦ ¦-------------------¦------------------------¦-------------------------------¦------------------------------------------------------------¦----------------------¦----------------------¦ Establishes how the project will be executed, monitored, controlled, and closed. Integrates all other plans. ¦ Project Management Plan ¦ Scope Management Plan, Schedule Management Plan, Cost Management Plan, Quality Management Plan, Resource Management Plan, Communications Plan, Risk Management Plan, Procurement Management Plan, Stakeholder Engagement Plan, Change Management Plan, Configuration Management Plan, Performance Measurement Baseline (scope, schedule, cost baselines), Development and lifecycle approach, Tailoring decisions ¦ Project Charter, Outputs from other planning processes, EEFs, OPAs ¦ Expert Judgment, Data Gathering (interviews), Interpersonal Skills, Meetings ¦ Final integrated plan before project execution begins. It is a living document updated via Perform Integrated Change Control. Approval required before proceeding to Execution phase. ¦